## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Construction of different components of Gajoldoba Tea Garden Piped Water Supply Scheme i.e, TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000071/2023-2024 | 422/A/JD | 07/06/2023 | 31/12/2025 | M/S SIBU DEY AND CO. | 262.74 | 89.62 | 34.11 | 20
2 | JALPAIGURI | Mal | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GAJOLDOBA TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000448/2023-2024 | 1387/NMD | 09/08/2023 | 01/03/2025 | SUBODH KUMAR BANIK | 27.14 | 12.21 | 45 | 70
3 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 1080/JD | 24/08/2023 | 24/08/2023 | Resource Division | 25.38 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Gajoldoba TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000317/2024-2025 | 2038/JD | 21/11/2024 | 19/02/2025 | M/S SIBU DEY AND CO. | 83.02 | 0 | 0 | 50
6 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Protective Boulder Work, Land Development and approach road inside the premises at H/W Site for Gajaldoba Tea Garden PWSS in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000478/2024-2025 | 2429/JD | 24/12/2024 | 07/02/2025 | M/S SIBU DEY AND CO. | 23.79 | 1.56 | 6.55 | 50
7 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.05.2024 to 30.06.2024)" | Assistant Engineer,HQ | Junior Engineer | ORD/000037/2024-2025 | 143/JD | 29/04/2024 | 29/06/2024 | GURUKUL INFOTECH | 3.16 | 3.16 | 100 | 100
8 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Laying Water Distribution Network in Gajoldoba Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000460/2024-2025 | 2426./JD | 24/12/2024 | 08/04/2025 | DINABANDHU ROY | 10.47 | 0 | 0 | 100
9 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Laying Water Distribution Network in Gajoldoba Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. (Port-B) | Assistant Engineer | Junior Engineer | ORD/000149/2024-2025 | 265/JSSD | 25/09/2024 | 09/03/2025 | JAGORAN SARKAR | 3.74 | 0 | 0 | 100
10 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 2025/JD | 09/01/2024 | 09/01/2024 | Resource Division | 12.26 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORK SITES OF DIFFERENT PWSS AT NAGRAKATA ,MATIALI , AND MAL BLOCK UNDER JALPAIGURI |  |  | BILL/00936/2024-2025 |  | 22/11/2024 | 22/11/2024 | DR. AMBARISH GHOSH | 17.82 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | New Service Connection Charge for GAJOLDOBA TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003425403 Reference ID : 403230603 |  |  | BILL/00453/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Infrastructure development cost for new service connection at GAJOLDOBA TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000110463 Reference ID : 860303003 |  |  | BILL/00452/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.41 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | New Service Connection Charge for GAJOLDOBA TG, TW NO-I, OODLABARI CCC APPLICATION NO. 4003425397 Reference ID : 403230604 |  |  | BILL/00455/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
15 | JALPAIGURI | Mal | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Infrastructure development cost for new service connection at GAJOLDOBA TG, TW NO-I, OODLABARI CCC APPLICATION NO. 100000110462 Reference ID : 860303002 |  |  | BILL/00454/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.65 | 0 | 0 | 0
16 | JALPAIGURI | Mal | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
17 | JALPAIGURI | Mal | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
18 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Sub-Soil Investigation of proposed 300 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Gajaldoba Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000801/2024-2025 | 88-HQ/JD | 11/03/2025 | 31/03/2025 | APEX ENGINEERING | 0.98 | 0 | 0 | 100
19 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | Material Requisition To Resource Division |  |  | RTOR000097/2024-2025 | 290/JD | 10/02/2025 | 10/02/2025 | Resource Division | 35.15 | 0 | 0 | 0
20 | JALPAIGURI | Mal | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15297 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORK SITES OF DIFFERENT PWSS AT NAGRAKATA ,MATIALI , AND MAL BLOCK UNDER JALPAIGURI |  |  | BILL/01415/2024-2025 | BP-2024-25-626 | 20/03/2025 | 20/03/2025 | DR. AMBARISH GHOSH | 6.42 | 0 | 0 | 0
Total | [13 empty] | 1042.59 | 106.55 | 10.22