## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme | SM/15298 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF KARBALA TG PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000414/2023-2024 | 1328/NMD | 08/08/2023 | 01/04/2026 | AHALYA ENGINEERING WORKS | 23.83 | 17.11 | 71.79 | 60
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme | SM/15298 | Augmentation | Construction of different components of Rejuvenation of Karbala Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000014/2023-2024 | 41/JD | 13/04/2023 | 02/05/2025 | MALAY BHOWMIK | 110.9 | 97.77 | 88.15 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme | SM/15298 | Augmentation | Sinking of Big dia Tube well 250x200mm dia using MS Slotted strainer at required depth by Reverse Rotary method of drilling for Karbala Tea Garden Pipe Water Supply Scheme in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000297/2023-2024 | 1355/JD | 26/09/2023 | 26/10/2023 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 20.38 | 15.96 | 78.31 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme | SM/15298 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1095/JD | 24/08/2023 | 24/08/2023 | Resource Division | 12.32 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme | SM/15298 | Augmentation | New Service Connection Charge for REJU KARBALA TEA GARDEN, T/W No. I, under BANARHAT CCC [APPLICATION NO. 4003333217 , Reference ID : 403157469] |  |  | BILL/02003/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.61 | 0 | 0 | 0
Total | [13 empty] | 172.05 | 130.84 | 76.05