## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | Construction of drain, development of land, Painting works of 250 Cu.M. capacity R.C.C. Elevated Reservoir, Pump House & Boundary Wall at Head works site for YongTong TG Piped Water Supply Scheme under Jalpaiguri Divition , P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000434/2022-2023 | 606/JD | 09/03/2023 | 08/04/2023 | PAMPA CONSTRUCTION | 6.2 | 6.16 | 99.29 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | Construction of different components for Rejuvenation of Yongtong Tea garden PWSS i.e. TW, Pump Housese, Boundary Wall, Water distribution Network, RISING MAIN etc. in connection with Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000087/2023-2024 | 439/JD. | 08/06/2023 | 29/11/2025 | ASHIS DUTTA | 69.4 | 0 | 0 | 50
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF YONGTONG TEA GARDEN AREA PWSS, TW NO III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000358/2023-2024 | 1318/NMD | 04/08/2023 | 30/06/2025 | RMD TRADING | 24.24 | 18.03 | 74.37 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 1100/JD | 24/08/2023 | 24/08/2023 | Resource Division | 14.64 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of YongTong Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000548/2023-2024 | 500/JSSD | 02/01/2024 | 01/02/2024 | D. S. ENTERPRISE | 2.34 | 2.29 | 98.12 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Yong Tong Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2024-2025 | 532/JD | 28/06/2024 | 28/07/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 26.33 | 79.24 | 100
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | "INFRA COST IRO NSC for (REJU) YONGTONG TG TW NO- IV, METELI CCC " APPLICATION NO.100000108225 Reference ID : 860300685 |  |  | BILL/00377/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.74 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | " New Service Connection Charge for (REJU) YONGTONG TG TW NO- IV, METELI CCC " APPLICATION NO.4003401347 Reference ID : 403212024 |  |  | BILL/00378/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | " New Service Connection Charge for (REJU) YONGTONG TG TW NO- III, METELI CCC " APPLICATION NO.4003419056 Reference ID : 403225904 |  |  | BILL/00376/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | "INFRA COST IRO NSC for (REJU) YONGTONG TG TW NO- III, METELI CCC " APPLICATION NO.100000108223 Reference ID : 860300683 |  |  | BILL/00375/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.72 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme | SM/15299 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000665/2025-2026 | 1084/HQ/NMD | 15/05/2025 | 22/05/2025 | D.K. & SONS | 0.79 | 0 | 0 | 0
Total | [13 empty] | 162.67 | 52.82 | 32.47