## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | Laying Distribution System (Part-L) along with 120 nos FHTC related to Rejuvenation of Nagrakata PWSS in connection with Jal Jeevan Mission at Block-Nagrakata under under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000353/2023-2024 | 294/JSSD | 27/09/2023 | 27/10/2023 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.68 | 0 | 0 | 60
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | EMERGENT REPAIRING OF PIPE LINE, R.B.T FIXING IN BOUNDARY WALL, INSTALLATION OF VALVE ALONG WITH OTHER ALLIED WORKS RELATED TO PIPELINE UNDER NAGRAKATA T.G. PIPE WATER SUPPLY SCHEME UNDER JALPAIGURI DIVISION, PHE DTE | Assistant Engineer | Junior Engineer | ORD/000354/2023-2024 | 301/JSSD | 27/09/2023 | 27/10/2023 | PARAMJYOTI ENTERPRISE | 5.37 | 0 | 0 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | Commissioning of Rejuvenation of Nagrakata Area Piped water supply Scheme under Jalpaiguri Division. P.H.E. Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000351/2023-2024 | 300/JSSD | 27/09/2023 | 27/10/2023 | PARAMJYOTI ENTERPRISE | 9.59 | 0 | 0 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 1058/JD | 24/08/2023 | 24/08/2023 | Resource Division | 11.54 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | "Deposite works,other than service connection for (REJU)NAGRAKATA TG TW NO-IV,NAGRAKATA CCC " APPLICATION NO.100000107213 Reference ID : 860298383 |  |  | BILL/00311/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.41 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | "New Service Connection Charge for (REJU)NAGRAKATA TG TW NO-IV,NAGRAKATA CCC " APPLICATION NO.4003390273 Reference ID : 403202824 |  |  | BILL/00310/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | "New Service Connection Charge for (REJU)NAGRAKATA TG TW NO-III,NAGRAKATA CCC " APPLICATION NO.4003390283 Reference ID : 403202825 |  |  | BILL/00312/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | "Deposite works,other than service connection for (REJU)NAGRAKATA TG TW NO-III,NAGRAKATA CCC " APPLICATION NO.100000107214 Reference ID : 860298384 |  |  | BILL/00313/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.32 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | Construction of different components for Rejuvenation of Nagrakata Tea garden PWSS i.e. TW, Pump Housese, Boundary Wall, Water distribution Network, RISING MAIN etc. in connection with Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000108/2023-2024 | 438/JD. | 08/06/2023 | 01/01/2025 | NARAYAN CHANDRA SAHA | 85.68 | 0 | 0 | 90
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAGRAKATA TG PWSS, TW no III & IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/001635/2023-2024 | 668/NMD | 15/03/2024 | 30/06/2025 | DEY ENTERPRISE(MALDA) | 24.07 | 0 | 0 | 95
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme | SM/15300 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.23 | 0 | 0 | 0
Total | [13 empty] | 161.25 | 0 | 0