## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | SM/15301 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Samsing T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000170/2020-2021 | 1304/JD | 24/11/2020 | 23/01/2021 | LOKNATH CONSTRUCTIOIN | 32.08 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | SM/15301 | Augmentation | Construction of different components of Rejuvenation of Samsing Tea Garden Piped Water Supply Scheme i.e TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc in connection with Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division,P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000140/2023-2024 | 698/JD | 13/07/2023 | 01/04/2026 | M/S. D.K. DEY & CO.. | 137.45 | 16.12 | 11.73 | 38
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | SM/15301 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SAMSING TG AREA PWSS, TW no III,IV,V,VI,VII in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000864/2023-2024 | 1810/NMD | 31/10/2023 | 01/11/2025 | M/S P.P. ELECTRICALS | 56.9 | 24.7 | 43.4 | 50
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | SM/15301 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 1070/JD | 24/08/2023 | 24/08/2023 | Resource Division | 19.77 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | SM/15301 | Augmentation | Balance work of Water Distribution Network in Chalsa Zone-I in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000838/2023-2024 | 1938/JD | 02/01/2024 | 01/02/2024 | ALICK DUTTA | 17.21 | 17.08 | 99.24 | 50
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | SM/15301 | Augmentation | "INFRA COST IRO NSC for (REJU) SAMSOING TG TW NO-III, METELI CCC " APPLICATION NO.100000107272 Reference ID : 860298682 |  |  | BILL/00323/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.79 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | SM/15301 | Augmentation | " New Service Connection Charge for (REJU) SAMSING TG TW NO- V, METELI CCC " APPLICATION NO.4003402758 Reference ID : 403213197 |  |  | BILL/00380/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | SM/15301 | Augmentation | "INFRA COST IRO NSC for (REJU) SAMSING TG TW NO- V, METELI CCC " APPLICATION NO.100000108221 Reference ID : 860300681 |  |  | BILL/00379/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.82 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme | SM/15301 | Augmentation | " New Service Connection Charge for (REJU) SAMSING TG TW NO-III, METELI CCC " APPLICATION NO.4003402763 Reference ID :403213198 |  |  | BILL/00327/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
Total | [13 empty] | 277.38 | 57.9 | 20.87