## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purba Duramari Piped Water Supply Scheme | SM/15326 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 1051/JD | 24/08/2023 | 24/08/2023 | Resource Division | 3.45 | 0 | 0 | 0
2 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Duramari Piped Water Supply Scheme | SM/15326 | Augmentation | New Service Connection Charge for new service connection at REJUVENATION OF PURBA DURAMARI PWSS,T/W-III, GAIRKATA CCC APPLICATION NO. 4003460491 Reference ID : 403255265 |  |  | BILL/00974/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Duramari Piped Water Supply Scheme | SM/15326 | Augmentation | Infrastructure development cost for new service connection at REJUVENATION OF PURBA DURAMARI PWSS,T/W-III, GAIRKATA CCC APPLICATION NO. 100000115667 Reference ID : 860308377 |  |  | BILL/00975/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.66 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purba Duramari Piped Water Supply Scheme | SM/15326 | Augmentation | Construction of different components of Rejuvenation of Purba Duramari PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000085/2023-2024 | 334/JD | 22/05/2023 | 19/05/2025 | MONTOSH GHOSH | 41.09 | 19.26 | 46.87 | 100
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Purba Duramari Piped Water Supply Scheme | SM/15326 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PURBA DURAMARI PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000182/2023-2024 | 1219/NMD | 26/07/2023 | 01/06/2025 | BONANZA ENTERPRISE | 11.5 | 7.78 | 67.68 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Purba Duramari Piped Water Supply Scheme | SM/15326 | Augmentation | Balance Laying Water Distribution Network including Providing Functional Household Tap Connection (FHTC) of Purba Duramari PWSS in connection with Jal Jeevan Mission at Block-Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000446/2024-2025 | 2320/JD | 11/12/2024 | 31/05/2025 | DEEP CONSTRUCTION | 13.08 | 0 | 0 | 100
Total | [13 empty] | 85.61 | 27.05 | 31.59