## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 1370/JD | 27/09/2023 | 27/09/2023 | Resource Division | 87.93 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN HANSKHALI PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000672/2023-2024 | 1487/NMD | 17/08/2023 | 16/09/2023 | HARA PROSAD DAS | 40.27 | 0 | 0 | 80
3 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 2016/JD | 09/01/2024 | 09/01/2024 | Resource Division | 17.2 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | New Service Connection Charge for DAKSHIN HANSKHALI,TW NO-I, KRANTI CCC APPLICATION NO. 4003445776 Reference ID : 403244353 |  |  | BILL/00521/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Infrastructure development cost for new service connection at DAKSHIN HANSKHALI,TW NO-I, KRANTI CCC APPLICATION NO. 100000112205 Reference ID : 860304705 |  |  | BILL/00520/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.93 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | New Service Connection Charge for DAKSHIN HANSKHALI,TW NO-II, KRANTI CCC APPLICATION NO. 4003445808 Reference ID : 403244351 |  |  | BILL/00518/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Infrastructure development cost for new service connection at DAKSHIN HANSKHALI,TW NO-II, KRANTI CCC APPLICATION NO. 100000112206 Reference ID : 860304706 |  |  | BILL/00519/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.16 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | New Service Connection Charge for DAKSHIN HANSKHALI,TW NO-III, KRANTI CCC APPLICATION NO. 4003445819 Reference ID : 403244352 |  |  | BILL/00517/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Infrastructure development cost for new service connection at DAKSHIN HANSKHALI,TW NO-III, KRANTI CCC APPLICATION NO. 100000112207 Reference ID : 860304707 |  |  | BILL/00516/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.52 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Construction of different components of Dakshin Hanskhali PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc.In connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000162/2023-2024 | 799/JD. | 24/07/2023 | 01/09/2026 | M/S. D.K. DEY & CO.. | 465.94 | 161.43 | 34.65 | 45
12 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Construction of Boundary Wall, Land Development, Pathway, Surface Drain etc. at H/W site of Dakshin Hanskhali PWSS i.c.w. Jal Jeevan Mission at block- Kranti under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000684/2024-2025 | 484/JD | 11/03/2025 | 25/04/2025 | M/S. D.K. DEY & CO.. | 21.14 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Dakshin Hanskhali PWSS 3rd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000102/2025-2026 | 481/RWS | 29/05/2025 | 28/06/2025 | GOURAV CONSTRUCTION CO. | 6.98 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
15 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Balance Laying Distribution Network and Providing Functional Household Tap connection (FHTC) including Construction of additional components of Dakshin Hanskhali PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000678/2024-2025 | 465/JD | 11/03/2025 | 10/05/2025 | M/S. D.K. DEY & CO.. | 74.53 | 0 | 0 | 0
16 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001008/2024-2025 | 28/NMD | 06/01/2025 | 05/02/2025 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0 | 0
17 | JALPAIGURI | Mal | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Dakshin Hanskhali PWSS 2nd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000104/2025-2026 | 482/RWS | 29/05/2025 | 28/06/2025 | M/S. D.K. DEY & CO.. | 8.36 | 0 | 0 | 0
18 | JALPAIGURI | Mal | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME | SM/15335 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
Total | [13 empty] | 1275.29 | 161.43 | 12.66