## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Construction of different components of Jhar Salbari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000041/2023-2024 | 139/JD | 28/04/2023 | 01/07/2025 | ALLIED INSTRUMENTS | 310.52 | 157.24 | 50.64 | 10
2 | JALPAIGURI | Dhupguri | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for JHAR SALBARI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000165/2023-2024 | 1207/NMD | 26/07/2023 | 01/11/2025 | SUBODH KUMAR BANIK | 20.26 | 0 | 0 | 60
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1111/JD | 24/08/2023 | 24/08/2023 | Resource Division | 20.09 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Material Requisition To Resource Division |  |  | RTOR000130/2023-2024 | 1844/JD | 15/12/2023 | 15/12/2023 | Resource Division | 8.57 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Jhar Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000425/2024-2025 | 2268/JD | 04/12/2024 | 18/01/2025 | J.M. CONSTRUCTION | 32.13 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | New Service Connection Charge for JHAR SHALBARI, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003364367 Reference ID : 403181756 |  |  | BILL/00131/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.75 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | New Service Connection Charge for JHAR SALBARI PWSS, TW no I, under DHUPGURI CCC APPLICATION NO. 4003543441 Reference ID : 403315624 |  |  | BILL/01672/2024-2025 | BP/24-25/249 | 13/12/2024 | 13/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.84 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001050/2024-2025 | 32/NMD | 06/01/2025 | 05/02/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Jalpaiguri Division | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Sinking of 3rd Tube well by Reverse Rotary Method of drilling inlucing Construction of Pump House (3.6m x 2.4m) and Laying Rising main for Jhar Salbari PWSS under Dhupguri Block icw Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000607/2024-2025 | 454/JD | 10/03/2025 | 29/04/2025 | M/S S. G. ENTERPRISE | 17.55 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
12 | JALPAIGURI | Dhupguri | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
13 | JALPAIGURI | Dhupguri | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME | SM/15742 | New | Additional New Service Connection Charge for JHAR SALBARI PWSS, at TW NO II, under DHUPGURI CCC APPLICATION NO. 100000133511 Reference ID : 860331001 |  |  | BILL/00318/2025-2026 |  | 19/05/2025 | 19/05/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.6 | 0 | 0 | 0
Total | [13 empty] | 1083.99 | 157.24 | 14.51