## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 157/JD | 28/04/2023 | 28/04/2023 | Resource Division | 12.08 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 1840/JD | 15/12/2023 | 15/12/2023 | Resource Division | 4.51 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SONAKHULI PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000239/2023-2024 | 1253/NMD | 31/07/2023 | 30/08/2023 | GOENKA ENTERPRISE | 20.65 | 14.24 | 68.97 | 60
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Sonakhuli Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000452/2024-2025 | 2332./JD | 12/12/2024 | 26/01/2025 | ABHIJIT SARKAR | 20.17 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Infrastructure development cost for new service connection at SONAKHULI,T/W-I, GAIRKATA CCC APPLICATION NO. 100000110438 Reference ID : 860302768 |  |  | BILL/00486/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.53 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Infrastructure development cost for new service connection at SONAKHULI,T/W-II, GAIRKATA CCC APPLICATION NO. 100000110437 Reference ID : 860302767 |  |  | BILL/00488/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.17 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | New Service Connection Charge for new service connection at SONAKHULI,T/W-I, GAIRKATA CCC APPLICATION NO. 4003424435 Reference ID : 403230061 |  |  | BILL/00485/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | New Service Connection Charge for new service connection at SONAKHULI,T/W-II, GAIRKATA CCC APPLICATION NO. 4003424430 Reference ID : 403230062 |  |  | BILL/00487/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Construction of different components of Sonakhuli PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000013/2023-2024 | 39/JD | 13/04/2023 | 03/07/2025 | JAYANTA GHOSH | 196.47 | 35.42 | 18.03 | 11
10 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001045/2024-2025 | 30/NMD | 06/01/2025 | 05/02/2025 | GEETA CONSTRUCTION | 12.33 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
12 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
13 | JALPAIGURI | Dhupguri | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME | SM/15744 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 914.9 | 49.66 | 5.43