## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | Emergency repairing of existing pipelines at different locations damaged due to road development works including cleaning chokages of blocked pipelines for smooth running of drinking water under Paschim Salbari (zone-I) water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000179/2022-2023 | 558/RWS | 01/09/2022 | 01/10/2022 | SAHA CONSTRUCTION | 3.5 | 0 | 0 | 1
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1114/JD | 24/08/2023 | 24/08/2023 | Resource Division | 9.67 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 1837/JD | 15/12/2023 | 15/12/2023 | Resource Division | 5.41 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PASCHIM SALBARI PWSS, ZONE-I, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000350/2023-2024 | 1311/NMD | 04/08/2023 | 03/09/2023 | DIAMOND ELECTRICAL WORKS | 21.32 | 0 | 0 | 50
5 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | New Service Connection Charge for PASCHIM SALBARI ZONE:- I, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003417554 Reference ID : 403224815 |  |  | BILL/00509/2024-2025 | BP/24-25/111 | 05/07/2024 | 05/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.9 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | New Service Connection Charge for PASCHIM SALBARI ZONE:- I, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003420142 Reference ID : 403226820 |  |  | BILL/00511/2024-2025 | BP/24-25/111 | 05/07/2024 | 05/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.31 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Paschim Salbari Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000608/2024-2025 | 635/JD | 28/03/2025 | 12/05/2025 | GOURAB GUHA ROY | 22.72 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001049/2024-2025 | 31/NMD | 06/01/2025 | 05/02/2025 | ANIMA ENTERPRISE | 15.32 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | Construction of different balance component of PASCHIM SALBARI ZONE-I PWSS i.e. Pump Houses, water distribution Network, OHR, Rising Main, FHTC etc.in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000240/2025-2026 | 2346/JD | 04/11/2025 | 04/03/2026 | MD HAKIMUDDIN | 227.97 | 0 | 0 | 0
12 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/15915 | New | Construction of different components of Paschim Salbari Zone- I PWSS i.e.TW, Pump Houses , Water distribution Network, OHR, RISING MAIN, FTHC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000046/2023-2024 | 239/JD | 08/05/2023 | 08/07/2024 | JAYANTA GHOSH | 242.01 | 0 | 0 | 12
Total | [13 empty] | 651.9 | 0 | 0