## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Nagrakata | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHHAR TANDU PWSS, TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000422/2023-2024 | 1336/NMD | 08/08/2023 | 07/09/2023 | THE BANERJEE CONCERN | 24.53 | 0 | 0 | 0
2 | JALPAIGURI | Nagrakata | Jalpaiguri Division | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3 | JALPAIGURI | Nagrakata | Jalpaiguri Division | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Construction of Boundary Wall at H/W site of Upper Tendu Forest (M) PWSS in connection with Jal Jeevan Mission at Block Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000540/2023-2024 | 295/JSSD | 27/09/2023 | 11/11/2023 | NISHITH RANJAN KARMAKAR | 7.99 | 7.96 | 99.64 | 100
4 | JALPAIGURI | Nagrakata | Jalpaiguri Division | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Construction of Boundary Wall at H/W site including rising main and interconnections of Tandu Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000013/2024-2025 | 474/JD | 21/06/2024 | 05/08/2024 | PRADIP SAHA | 15.98 | 16.2 | 101.41 | 100
5 | JALPAIGURI | Nagrakata | Jalpaiguri Division | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Sinking of 2 (Two) Nos. Big Dia Tube well by Modified DTH - ODEX Method at 1st & 2nd tube well site of Chhar Tandu and adjacent area Piped Water Supply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000110/2024-2025 | 1415/JD | 20/09/2024 | 20/10/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 35.23 | 27.63 | 78.44 | 100
6 | JALPAIGURI | Nagrakata | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001003/2024-2025 | 23/NMD | 06/01/2025 | 05/02/2025 | SARKAR ELECTRIC | 15.78 | 0 | 0 | 0
7 | JALPAIGURI | Nagrakata | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.23 | 0 | 0 | 0
8 | JALPAIGURI | Nagrakata | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
9 | JALPAIGURI | Nagrakata | Jalpaiguri Division | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Balance work in connection with Laying distribution system along with providing FHTC at Tandu Piped W/S Scheme in connection with JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000151/2024-2025 | 269/JSSD | 25/09/2024 | 02/01/2025 | PRADIP SAHA | 7.52 | 0 | 0 | 100
10 | JALPAIGURI | Nagrakata | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Deposite work other than service connection for CHHAR TANDU PWSS TW-II(SULKAPARA FATU LINE) Reference Id-860319609 Application no-100000124539 |  |  | BILL/01674/2024-2025 | BP/24-25/249 | 13/12/2024 | 13/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.97 | 0 | 0 | 0
11 | JALPAIGURI | Nagrakata | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | New service connection charge for CHHAR TANDU PWSS TW-II(SULKAPARA FATU LINE) Reference Id-403319115 Application no-4003548502 |  |  | BILL/01675/2024-2025 | BP/24-25/249 | 13/12/2024 | 13/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
12 | JALPAIGURI | Nagrakata | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | New service connection charge for CHHAR TANDU PWSS TW-I(SULKAPARA PATWWARI PARA) Reference Id-403321506 Application no-4003551825 |  |  | BILL/01886/2024-2025 | BP/24-25/250 | 21/01/2025 | 21/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
13 | JALPAIGURI | Nagrakata | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Deposite work other than service connection For CHHARTANDU PWSS TW-I(SULKAPARA ,PATWWARI PARA) Reference Id-860318866 Application no-100000124656 |  |  | BILL/01887/2024-2025 | BP/24-25/250 | 21/01/2025 | 21/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.27 | 0 | 0 | 0
14 | JALPAIGURI | Nagrakata | Jalpaiguri Division | CHHAR TANDU PIPED WATER SUPPLY SCHEME | SM/15964 | New | Laying Distribution System along with laying of Rising Main, Pump Connection & Construction of 2 Nos. Pump House at 1st & 2nd Tube Well Site of Adjacent area of Chhar Tandu and Adjacent area Piped Water Sypply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000465/2025-2026 | 2498/JD | 09/12/2025 | 08/05/2026 | ARUP SARKAR | 36.8 | 0 | 0 | 20
Total | [13 empty] | 733.89 | 51.8 | 7.06