## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Construction of differet components of Baragharia Zone-II PWSS i.e TW, Pump Houses, Water distribution Network, OHR, Boundary Wall, RISING MAIN, FHTC etc. in connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000053/2023-2024 | 357/JD. | 25/05/2023 | 21/11/2023 | M.S ENTERPRISE | 166.28 | 64.33 | 38.69 | 65
2 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Construction of differet components of Baragharia Zone-I PWSS i.e TW, Pump Houses , Water distribution Network, OHR, Boundary Wall , RISING MAIN , FHTC etc. in connection with Jal Jeevan Mission at Block Kranti under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 356/JD | 25/05/2023 | 01/10/2025 | M.S ENTERPRISE | 246.82 | 113.98 | 46.18 | 40
3 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 1078/JD | 24/08/2023 | 24/08/2023 | Resource Division | 38.3 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA GHARIA PWSS at TW NO I,II, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001570/2023-2024 | 654/NMD | 15/03/2024 | 01/04/2025 | SUBHRANGSHU GUHARAJA | 23.9 | 14.06 | 58.83 | 50
5 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Material Requisition To Resource Division |  |  | RTOR000204/2023-2024 | 2074/JD | 10/01/2024 | 10/01/2024 | Resource Division | 8.03 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Infrastructure development cost for new service connection at BARA GHARIA,TW NO-II, KRANTI CCC APPLICATION NO. 100000109538 Reference ID : 860301298 |  |  | BILL/00406/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.51 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Infrastructure development cost for new service connection at BARA GHARIA ,ZONE-II,TW-II, MAL CCC APPLICATION NO. 100000117355 Reference ID : 860311645 |  |  | BILL/01423/2024-2025 | BP/24-25/240 | 30/10/2024 | 30/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.68 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | New Service Connection Charge for BARA GHARIA,TW NO-I, KRANTI CCC APPLICATION NO. 4003426904 Reference ID : 403231622 |  |  | BILL/00408/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | New Service Connection Charge for BARA GHARIA ,ZONE-II,TW-II, MAL CCC APPLICATION NO. 4003477836 Reference ID : 403266830 |  |  | BILL/01421/2024-2025 | BP/24-25/240 | 30/10/2024 | 30/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | New Service Connection Charge for BARA GHARIA ,ZONE-II,TW-I, MAL CCC APPLICATION NO. 4003477826 Reference ID : 403266831 |  |  | BILL/01422/2024-2025 | BP/24-25/240 | 30/10/2024 | 30/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Infrastructure development cost for new service connection at BARA GHARIA,TW NO-I, KRANTI CCC APPLICATION NO. 100000109544 Reference ID : 860302004 |  |  | BILL/00405/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.98 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | New Service Connection Charge for BARA GHARIA,TW NO-II, KRANTI CCC APPLICATION NO. 4003426943 Reference ID : 403231623 |  |  | BILL/00407/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Infrastructure development cost for new service connection at BARA GHARIA ,ZONE-II,TW-I, MAL CCC APPLICATION NO. 100000117353 Reference ID : 860311643 |  |  | BILL/01420/2024-2025 | BP/24-25/240 | 30/10/2024 | 30/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.85 | 0 | 0 | 0
15 | JALPAIGURI | Mal | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME | SM/15967 | New | Construction of Additional Components for uncovered TANTY PARA AREA of BARAGHARIA PWSS i.e. TW, Pump House ,Boundary Wall, Water distribution Network ,FHTC, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000543/2024-2025 | 570/JD | 25/03/2025 | 08/06/2025 | SADHAN KARMAKAR | 113.85 | 0 | 0 | 0
Total | [13 empty] | 653.57 | 192.37 | 29.43