## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | TESIMALA PIPED WATER SUPPLY SCHEME | SM/15970 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | TESIMALA PIPED WATER SUPPLY SCHEME | SM/15970 | New | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 2014/JD | 09/01/2024 | 09/01/2024 | Resource Division | 7.02 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Northern Mechanical | TESIMALA PIPED WATER SUPPLY SCHEME | SM/15970 | New | New Service Connection Charge for TESIMLA, TW NO-II, MAL CCC APPLICATION NO. 4003352318 Reference ID : 403172835 |  |  | BILL/00202/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Northern Mechanical | TESIMALA PIPED WATER SUPPLY SCHEME | SM/15970 | New | New Service Connection Charge for TESIMLA, TW NO-I, MAL CCC APPLICATION NO. 4003352315 Reference ID : 403172834 |  |  | BILL/00201/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | TESIMALA PIPED WATER SUPPLY SCHEME | SM/15970 | New | Infrastructure development cost for new service connection at TESIMLA,, TW NO-I & II, MAL CCC APPLICATION NO. 100000102139 Reference ID : 860293899 |  |  | BILL/00203/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.86 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Jalpaiguri Division | TESIMALA PIPED WATER SUPPLY SCHEME | SM/15970 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including different components of Tesimala PWSS i.e. Tube Well, Pump House, Boundary Wall in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000547/2024-2025 | 104/JD | 15/01/2025 | 26/03/2025 | APEX ENGINEERING | 39.7 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | TESIMALA PIPED WATER SUPPLY SCHEME | SM/15970 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for TESIMLA PWSS, TW no I & II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000328/2023-2024 | 1299/NMD | 03/08/2023 | 01/03/2025 | SUMON ELECTRICAL | 23.05 | 19 | 82.4 | 100
Total | [13 empty] | 109.65 | 19 | 17.33