## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | Sinking of 1 (One) No Modified Big Dia Tube Well 250 X 200 mm dia using MS Slotted Strainer at required depth by Reverse Rotary method of drilling at Meanglass Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000106/2024-2025 | 1416/JD | 20/09/2024 | 10/10/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 20.88 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | Sinking of Modified Big Dia Tube Well 250 X 200 mm dia using MS Slotted Strainer at required depth by Reverse Rotary method of drilling for one no. tube well at Meenglass Tea Garden Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000468/2023-2024 | 1761/JD | 08/12/2023 | 23/12/2023 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 20.46 | 19.19 | 93.79 | 100
4 | JALPAIGURI | Mal | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | Material Requisition To Resource Division |  |  | RTOR000202/2023-2024 | 2072/JD | 10/01/2024 | 10/01/2024 | Resource Division | 6.75 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | New Service Connection Charge for MENGLASS TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266406, Reference ID : 403105525] |  |  | BILL/01279/2023-2024 | 23-24/158&166 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | New Service Connection Charge for MENGLASS TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003424052 Reference ID : 403230050 |  |  | BILL/00412/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | Infrastructure development cost for new service connection at MENGLASS TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000109304 Reference ID : 860301264 |  |  | BILL/00411/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.47 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | Infrastructure Cost for MENGLASS TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093891, Reference ID : 860285651] |  |  | BILL/01280/2023-2024 | 23-24/158&166 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.72 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | Construction of different components of Menglass Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2023-2024 | 40/JD | 13/04/2023 | 08/12/2024 | SANDIP BANIK | 206.82 | 125.67 | 60.76 | 100
13 | JALPAIGURI | Mal | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/15990 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MENGLASS TEA GARDEN PWSS, TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000454/2023-2024 | 1393/NMD | 09/08/2023 | 01/05/2025 | M/S SAJAHAN CHOWDHURY | 24.55 | 13.84 | 56.37 | 100
Total | [13 empty] | 840.51 | 158.7 | 18.88