## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 | New | Arrangement for disposal of waste water of IEP at H/W site of Paschim Salbari(zone-II) W/S/S under Jalpaiguri Division , P.H.E. Dte. |  |  | ORD/000284/2022-2023 | 649/RWS | 21/10/2022 | 10/11/2022 | PARAMJYOTI ENTERPRISE | 4.32 | 0 | 0 | 1
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 | New | Construction of diferent components of Paschim Salbari Zone-II pwss i.e TW, Pump Houses, water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division , P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000058/2023-2024 | 264/JD | 10/05/2023 | 01/04/2026 | ANUP SARKAR | 213 | 163.63 | 76.82 | 35
3 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PASCHIM SALBARI PWSS, ZONE-II, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000167/2023-2024 | 1209/NMD | 26/07/2023 | 24/06/2025 | THE BANERJEE CONCERN | 21.54 | 10.19 | 47.32 | 100
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1113/JD | 24/08/2023 | 24/08/2023 | Resource Division | 9.93 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 | New | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 1880/JD | 20/12/2023 | 20/12/2023 | Resource Division | 4.77 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Paschim Salbari Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000457/2024-2025 | 2333./JD | 12/12/2024 | 01/04/2026 | ANUP SARKAR | 18.22 | 0 | 0 | 100
7 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 | New | New Service Connection Charge for PASCHIM SALBARI PWSS, ZONE-II, TW NO II, under DHUPGURI CCC APPLICATION NO. 4003289711 Consumer ID : 403122966 |  |  | BILL/00535/2024-2025 | BP/24-25/130 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.75 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 | New | New Service Connection Charge for PASCHIM SALBARI ,ZONE:-II, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003379309 Reference ID : 403193837 |  |  | BILL/00307/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.77 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001049/2024-2025 | 31/NMD | 06/01/2025 | 05/02/2025 | ANIMA ENTERPRISE | 15.32 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/16040 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 847.21 | 173.82 | 20.52