## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 1884/JD | 20/12/2023 | 20/12/2023 | Resource Division | 14.51 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). |  |  | ORD/000295/2023-2024 | 855/JD | 31/07/2023 | 31/01/2024 | SOUMEN GHOSH | 0.88 | 0 | 0 | 20
3 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Continuation for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit)." | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000570/2023-2024 | 2197/JD | 25/01/2024 | 25/07/2024 | SOUMEN GHOSH | 0.88 | 0.56 | 63.84 | 0
4 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 05/10/2024 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 0 | 90
5 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 2016/JD | 19/11/2024 | 19/11/2024 | Resource Division | 156.48 | 0 | 0 | 0
6 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of October 2024. |  |  | BILL/00938/2024-2025 | BP-2024-25-525 | 29/11/2024 | 29/11/2024 | FILL & SMILE | 0.13 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-II, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003351981, Reference ID : 403172665] |  |  | BILL/02147/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.85 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-II, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341742, Reference ID : 403172228] |  |  | BILL/02146/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.01 | 0 | 0 | 0
9 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Construction of different components of Barapatina Nutanbus Zone-II PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000128/2023-2024 | 408/A/JD | 07/06/2023 | 12/05/2025 | UNIBRO INFRASERV PRIVATE LIMITED | 434.44 | 213.71 | 49.19 | 70
10 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Distribution System and Functional Household Tap Connection (FHTC) for Barapatina Nutunbas Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 736/JD | 26/07/2024 | 01/01/2026 | MOTI INDUSTRIES | 128.89 | 82.7 | 64.17 | 85
11 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at BARAPATINA NATUNBUS PWSS for T/W No. I and II, ZONE-II in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000843/2024-2025 | 582/NMD | 07/02/2025 | 09/03/2025 | SARKAR ELECTRIC | 23.55 | 0 | 0 | 0
12 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000101/2024-2025 | 874/JD | 31/07/2024 | 31/01/2025 | SOUMEN GHOSH | 0.88 | 0.44 | 50 | 0
13 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001001/2024-2025 | 22/NMD | 06/01/2025 | 05/02/2025 | SUMON ELECTRICAL | 12.23 | 0 | 0 | 0
14 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Barapatina Nutanbus Zone-II PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000011/2025-2026 | 895/JD | 08/05/2025 | 17/06/2025 | PRADIP KUMAR SHIL | 18.52 | 0 | 0 | 0
15 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site BARAPATINA NATUNBUS ZONE -II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000106/2025-2026 | 484/RWS | 29/05/2025 | 01/04/2026 | JAYA SARKAR | 8.04 | 0 | 0 | 0
16 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
17 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri RWS Sub Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer | Junior Engineer | ORD/000033/2025-2026 | 820/JD | 30/04/2025 | 30/06/2025 | SUKES BASU MAJUMDAR | 0.8 | 0 | 0 | 0
18 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri RWS Sub Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer | Junior Engineer | ORD/000123/2025-2026 | 1499/JD | 30/06/2025 | 31/07/2025 | SUKES BASU MAJUMDAR | 0.4 | 0 | 0 | 0
19 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME | SM/16041 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 1421.64 | 297.42 | 20.92