## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1108/JD | 24/08/2023 | 24/08/2023 | Resource Division | 9.53 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | Material Requisition To Resource Division |  |  | RTOR000131/2023-2024 | 1845/JD | 15/12/2023 | 15/12/2023 | Resource Division | 8.44 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | New Service Connection Charge for CHARCHARABARI, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003365758 Reference ID : 403183039 |  |  | BILL/00129/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.21 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | New Service Connection Charge for CHARCHARABARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003364338 Reference ID : 403181777 |  |  | BILL/00130/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.23 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | Construction of different components of Char Charabari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block ¿ Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000051/2023-2024 | 243JD | 08/05/2023 | 09/05/2025 | SRINIWAS AGARWAL | 328.17 | 0 | 0 | 50
6 | JALPAIGURI | Dhupguri | Jalpaiguri Division | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | Balance work of distribution system and Functional House Hold Tap Connection (FHTC) including Construction of Boundary wall, drain, footpath at 2 nd site of Charchara Bari PWSS at Banarhat Block under Jalapiguri Division PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000459/2024-2025 | 2345/JD | 12/12/2024 | 10/02/2025 | SRINIWAS AGARWAL | 70.88 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001050/2024-2025 | 32/NMD | 06/01/2025 | 05/02/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Jalpaiguri Division | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Char Chara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000586/2024-2025 | 634/JD | 28/03/2025 | 12/05/2025 | JITENDRA NATH ROY | 30.36 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME | SM/16042 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHARCHARABARI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000166/2023-2024 | 1208/NMD | 26/07/2023 | 01/04/2025 | M/S CHANDRANATH MUKHERJEE | 22.17 | 0 | 0 | 100
Total | [13 empty] | 1132.2 | 0 | 0