## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KURTI TEA GARDEN PWSS(TW No- I, II and III), in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000860/2023-2024 | 1804/NMD | 31/10/2023 | 30/11/2023 | SARKAR ELECTRIC | 37.45 | 0 | 0 | 0
2 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 167/JD | 28/04/2023 | 28/04/2023 | Resource Division | 56.03 | 0 | 0 | 0
3 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Construction of different components of Kurti Tea Garden (Zone-I, II and III) PWSS i.e, TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2023-2024 | 263/JD | 10/05/2023 | 06/11/2023 | S. N. POLYMERS PVT. LTD. | 308.54 | 0 | 0 | 0
4 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 2038/JD | 09/01/2024 | 09/01/2024 | Resource Division | 6.64 | 0 | 0 | 0
5 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
6 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001003/2024-2025 | 23/NMD | 06/01/2025 | 05/02/2025 | SARKAR ELECTRIC | 15.78 | 0 | 0 | 0
7 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN | SM/16492 | New | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.23 | 0 | 0 | 0
Total | [13 empty] | 461.7 | 0 | 0