## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16508 | Support-WQMSP | Procurement of Chemicals, Consumables for 04 No's laboratories under Jalpaiguri Division PHE Dte. |  |  | ORD/000450/2022-2023 | 721/JD | 20/03/2023 | 19/04/2023 | ARUNALOY SCIENTIFIC HOUSE | 9.87 | 9.87 | 100 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16508 | Support-WQMSP | Procurement of necessary Chemicals and consumables for regular & NABL related water sample testing purpose of Laboratories under Jalpaiguri Division. PHE. Dte.for one month. | Assistant Engineer | Junior Engineer | ORD/000078/2024-2025 | 734/RWS | 02/08/2024 | 02/09/2024 | ARUNALOY SCIENTIFIC HOUSE | 0.97 | 0.97 | 100 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16508 | Support-WQMSP | Honorarium of the LAB personnel & Maintenance Charge of The Laboratory for October, November & December 2023 from Office memo No-RWO/L/05 Date-19/12/2023 and Govt Memo no-PHE/WSSO/112/2827-2844 date-07/12/2015 for draft Mou regarding the agreement between NGO managing water testing laboratory & PHED,Govt. of west Bengal and ORDER no-27552-27581/MC/LABS/000007/2021 Date-14/12/2022 for Enhancement of Monthly remuneration of lab personal and fund thereto |  |  | BILL/01232/2023-2024 | BP-2023-24-662 | 20/02/2024 | 20/02/2024 | RAJGANJ WELLFEAR ORGANISATION | 1.54 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16508 | Support-WQMSP | Work of Operation of Chalsa Laboratory at Chalsa PWSS premises for Physical, Chemical and Bacteriological test of water sample under Jalpaiguri Division, PHE Dte. From 1st February 2023 to 31st January 2024. | Assistant Engineer | Junior Engineer | ORD/000173/2023-2024 | 865/JD | 01/08/2023 | 01/08/2024 | SUKES BASU MAJUMDAR | 5.22 | 3.57 | 68.35 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16508 | Support-WQMSP | Procurement of necessary Chemicals (having 2 years shelve life from date of supply) for Regular & NABL related water sample testing purpose for 4 No Laboratories (including 1 No NGO Managed) under Jalpaiguri Division, PHE Dte. for 12 months. | Assistant Engineer | Junior Engineer | ORD/000119/2024-2025 | 1380/JD | 18/09/2024 | 03/10/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 15.29 | 15.29 | 100 | 100
Total | [13 empty] | 32.88 | 29.69 | 90.3