## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Continuation order Honorarium for of Running District Laboratory staff for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division office P.H.E. Dte.for 4 Months from 01/08/2022 to 30/11/2022 |  |  | ORD/000422/2022-2023 | 476/RWS | 25/07/2022 | 25/11/2022 | R.S CONSTRUCTION | 3.08 | 3.08 | 100 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Further Continuation order Honorarium for of Running District Laboratory staff for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division office P.H.E. Dte.for 4 Months from 01/12/2022 to 31/03/2023 |  |  | ORD/000455/2022-2023 | 658/RWS | 07/11/2022 | 07/03/2023 | R.S CONSTRUCTION | 2.8 | 2.8 | 100 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Continuation order for Work of Running Dhupguri Laboratory at Dhupguri PWSS Premie for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division P.H.E. Dte.for 4 Months from 01-10-2022 to 31.01.2023. |  |  | ORD/000593/2022-2023 | 617/RWS | 29/09/2022 | 29/01/2023 | SUKES BASU MAJUMDAR | 1.08 | 1.08 | 100 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Further Continuation order Honorarium fur of Running District Laboratory staff for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division office P.H.E. Dte.for 3 Months from 01/04/2023 to 30/06/2023 |  |  | ORD/000592/2022-2023 | 308/RWS | 31/03/2023 | 30/06/2023 | R.S CONSTRUCTION | 2.1 | 2.1 | 100 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Continuation order for Work of Running Chalsa Laboratory at Chalsa PWSS Premie for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division P.H.E. Dte. for 4 Months from 01-10-2022 to 31-01-2023 |  |  | ORD/000594/2022-2023 | 618/RWS | 29/09/2022 | 29/01/2023 | SUKES BASU MAJUMDAR | 1.08 | 1.08 | 100 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Continuation order for Work of Running Dhupguri Laboratory at Dhupguri zone - ii PWSS Premises for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division P.H.E. Dte. for 6 Months from 01-02-2023 to 31-07-2023. |  |  | ORD/000622/2022-2023 | 74/RWS | 31/01/2023 | 31/07/2023 | SUKES BASU MAJUMDAR | 1.69 | 1.69 | 100 | 100
7 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Continuation order for Work of Running Chalsa Laboratory at Chalsa PWSS Premie for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division P.H.E. Dte. for 6 Months from 01-02-2023 to 31-07-2023. |  |  | ORD/000624/2022-2023 | 73/RWS | 31/01/2023 | 31/07/2023 | SUKES BASU MAJUMDAR | 1.69 | 1.69 | 100 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Continuation order for Organizing the updating and synchronization of different data related with laboratory, PWSS etc. in connection with Jalswapna under Jalpaiguri division PHE Dte. for 2 Months from 01/05/2023 to 30/06/2023 |  |  | ORD/000324/2023-2024 | 435/RWS | 28/04/2023 | 28/06/2023 | R.S CONSTRUCTION | 0.27 | 0.27 | 100 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Continuation order for Organizing the updating and synchronization of different data related with laboratory, PWSS etc. in connection with Jalswapna under Jalpaiguri division PHE Dte. for 3 Months from 01/05/2023 to 30/06/2023 |  |  | ORD/000116/2023-2024 | 435/RWS | 28/04/2023 | 28/06/2023 | R.S CONSTRUCTION | 0.27 | 0 | 0 | 100
10 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Festival bonus for laboratory personnel for the financial year 2022-2023 |  |  | BILL/00573/2023-2024 | BP-2023-24-395 | 29/09/2023 | 29/09/2023 | RAJGANJ WELLFEAR ORGANISATION | 0.16 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | HONORARIUM OF THE LAB PERSONNEL & MAINTAINENCE CHARGE OF THE LAB FOR THE MONTH OF APRIL MAY JUNE 2023 |  |  | BILL/00214/2023-2024 | BP-2023-24-224 | 17/07/2023 | 17/07/2023 | RAJGANJ WELLFEAR ORGANISATION | 1.54 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | T.A of transportation of referral sample of Dist lab of Jalpaiguri and other Sub Dist labs & N.G.O .managed lab of Jalpaiguri to Mangal Pandey Referral lab. |  |  | BILL/00364/2023-2024 | BP-2023-24-329 | 25/08/2023 | 25/08/2023 | SUJIT BASU | 0.06 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Honorarium of the lab personnel and maintenance charge of the laboratory for January, February & March of Rajganj Welfare Organization,P.O- Rajganj,Dist-Jalpaiguri(Government of West Bengal Supported Rural Drinking Water Testing Laboratory) Registration No-S/83259,ESTD-1992 Ref No-RWO/L/06 Dated-27.03.2024 |  |  | BILL/00098/2024-2025 | BP-2024-25-65 | 14/05/2024 | 14/05/2024 | RAJGANJ WELLFEAR ORGANISATION | 1.54 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION | SM/16509 | Support-WQMSP | Work of Operation for Dhupguri Laboratory at Dhupguri Zone-II PWSS premises Physical, Chemical and Bacteriological test of water sample under Jalpaiguri Division, PHE Dte. From 1st February 2023 to 31st January 2024. | Assistant Engineer | Junior Engineer | ORD/000174/2023-2024 | 864/JD | 01/08/2023 | 01/08/2024 | B.M CONSTRUCTION | 5.01 | 0 | 0 | 100
Total | [13 empty] | 22.36 | 13.79 | 61.66