## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 156/JD | 28/04/2023 | 28/04/2023 | Resource Division | 16.82 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Material Requisition To Resource Division |  |  | RTOR000135/2023-2024 | 1882/JD | 20/12/2023 | 20/12/2023 | Resource Division | 4.11 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Construction of different components of Bhemtia PWSS i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000005/2023-2024 | 02/JD | 06/04/2023 | 08/11/2025 | SCEC BOENTER KDAS JOINT VENTURE | 209.41 | 0 | 0 | 30
4 | JALPAIGURI | Dhupguri | Northern Mechanical | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001050/2024-2025 | 32/NMD | 06/01/2025 | 05/02/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Sub-Soil Investigation including liquefaction due to close proximity of railway track near the proposed 100 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Bhemtia Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000803/2024-2025 | 93-HQ/JD | 17/03/2025 | 06/04/2025 | R.B TESTING | 0.98 | 0 | 0 | 0
Total | [13 empty] | 335.42 | 0 | 0