## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Construction of different components of Bhemtia PWSS i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000005/2023-2024 | 02/JD | 06/04/2023 | 03/10/2023 | SCEC BOENTER KDAS JOINT VENTURE | 209.41 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Northern Mechanical | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BHEMTIA PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000067/2023-2024 | 632/NMD | 24/05/2023 | 23/06/2023 | UTTAM PAUL | 21.88 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Dhupguri, Rajganj and Balance of Banarhat Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2024-2025 | 940/JD | 07/08/2024 | 06/10/2024 | AKG UDYOG | 25.37 | 0 | 0 | 45
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 156/JD | 28/04/2023 |  | Resource Division | 16.82 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | Material Requisition To Resource Division |  |  | RTOR000135/2023-2024 | 1882/JD | 20/12/2023 |  | Resource Division | 4.11 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | New Service Connection Charge for BHEMTIA PWSS, TW NO I, under DHUPGURI CCC . APPLICATION NO. 4003444910 Reference ID : 403243717 |  |  | BILL/01502/2024-2025 | null | 02/12/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 20.12 | 0 | 0 | null
7 | JALPAIGURI | Dhupguri | Northern Mechanical | BHEMTIA PIPED WATER SUPPLY SCHEME | SM/16676 | New | New Service Connection Charge for BHEMTIA PWSS, TW NO II, under DHUPGURI CCC. APPLICATION NO. 4003444915 Reference ID : 403243716 |  |  | BILL/01503/2024-2025 | null | 02/12/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.38 | 0 | 0 | null
Total | [13 empty] | 309.08 | 0 | 0