## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme | SM/16772 | Augmentation | Construction of different components of Rejuvenation Of Haritalguri Tea Garden Area PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000131/2023-2024 | 418/A/JD | 07/06/2023 | 06/08/2023 | M/S ROY & SARKAR CONSTRUCTION | 69.21 | 20.04 | 28.95 | 11
2 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme | SM/16772 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HARITALGURI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , TW No III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000451/2023-2024 | 1390/NMD | 09/08/2023 | 01/02/2025 | SUBHRA ENTERPRISE | 11.7 | 2.95 | 25.24 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme | SM/16772 | Augmentation | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Banarhat block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer | Junior Engineer | ORD/000451/2023-2024 | 1288/RWS | 28/11/2023 | 28/12/2023 | SUKES BASU MAJUMDAR | 3.11 | 3.11 | 100 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme | SM/16772 | Augmentation | Balance work of Laying pipeline & providing FHTC with allied works at Haritalguri Piped Water Supply Scheme in connection with JJM within Banarhat Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000487/2024-2025 | 2425/JD | 24/12/2024 | 07/02/2025 | M/S ROY & SARKAR CONSTRUCTION | 32.68 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme | SM/16772 | Augmentation | New Service Connection Charge for HARITALGURI, T/W No. III, under BANARHAT CCC [APPLICATION NO. 4003332995 , Reference ID : 403157461] |  |  | BILL/02001/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.07 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme | SM/16772 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme | SM/16772 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 726.9 | 26.1 | 3.59