## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/16773 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , TW No III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000357/2023-2024 | 1319/NMD | 04/08/2023 | 28/02/2025 | EASTERN INDIA SALES & SERVICE | 20.6 | 0 | 0 | 70
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/16773 | Augmentation | Construction of different components of Rejuvenation of Batabari Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000315/2023-2024 | 1347/JD | 26/09/2023 | 16/04/2025 | SABITA ENTERPRISE | 127.56 | 79.84 | 62.59 | 52
3 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/16773 | Augmentation | "New Service Connection Charge fo(REJU) BATABARI TG PWSS TW NO-III, METELI CCC " APPLICATION NO.4003385771 Reference ID : 403199268 |  |  | BILL/00391/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/16773 | Augmentation | "New Service Connection Charge fo(REJU) BATABARI TG PWSS TW NO-IV, METELI CCC " APPLICATION NO.4003386376 Reference ID : 403200294 |  |  | BILL/00390/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/16773 | Augmentation | "INFRA COST IRO NSC for (REJU) BATABARI TG PWSS TW NO-IV, METELI CCC " APPLICATION NO.100000105522 Reference ID : 860297572 |  |  | BILL/00248/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.99 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/16773 | Augmentation | "INFRA COST IRO NSC for (REJU) BATABARI TG PWSS TW NO-III, METELI CCC " APPLICATION NO.100000105525 Reference ID : 860297575 |  |  | BILL/00247/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.24 | 0 | 0 | 0
Total | [13 empty] | 166.76 | 79.84 | 47.88