## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Northern Mechanical | PURBA DOBBARI PIPED WATER SUPPLY SCHEME | SM/16776 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PURBA DOBBARI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000427/2023-2024 | 1344/NMD | 08/08/2023 | 07/09/2023 | S.D. CONCERN | 6.11 | 0 | 0 | 0
2 | JALPAIGURI | Maynaguri | Jalpaiguri Division | PURBA DOBBARI PIPED WATER SUPPLY SCHEME | SM/16776 | New | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 2054/JD | 09/01/2024 | 09/01/2024 | Resource Division | 0.18 | 0 | 0 | 0
3 | JALPAIGURI | Maynaguri | Jalpaiguri Division | PURBA DOBBARI PIPED WATER SUPPLY SCHEME | SM/16776 | New | Construction of different components of Purba Dobbari PWSS i.e. TW, Pump Houses, Water distribution Network, Stand alone Mini OHR, RISING MAIN, FHTC etc.i.c.w. Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2023-2024 | 946/JD | 08/08/2023 | 01/07/2025 | SOMNATH ROY | 38.25 | 0 | 0 | 70
4 | JALPAIGURI | Maynaguri | Northern Mechanical | PURBA DOBBARI PIPED WATER SUPPLY SCHEME | SM/16776 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
Total | [13 empty] | 137.61 | 0 | 0