## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 1077/JD | 24/08/2023 | 24/08/2023 | Resource Division | 35.1 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 1886/JD | 20/12/2023 | 20/12/2023 | Resource Division | 13.79 | 0 | 0 | 0
3 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 1508/JD | 13/10/2023 | 13/10/2023 | Resource Division | 13.79 | 0 | 0 | 0
4 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit). | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000122/2023-2024 | 383/A/JD | 01/06/2023 | 01/12/2023 | RUPA PRASAD | 0.88 | 0.38 | 43.05 | 50
5 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.12.2023 to 31.05.2024)". | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000533/2023-2024 | 1677/JD | 24/11/2023 | 24/05/2024 | RUPA PRASAD | 0.88 | 2.11 | 239.36 | 100
6 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 05/10/2024 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 0 | 90
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | New Service Connection Charge for new service connection at PAHARPUR, T/W-I, ZONE-II, UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003427350 Reference ID : 403231842 |  |  | BILL/00481/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.78 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Construction of different components of Paharpur Zone - II PWSS i.e TW, pump houses,water distribution network, OHR, Rising Main, FHTC etc. at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000050/2023-2024 | 130/JD | 28/04/2023 | 03/04/2025 | GARGO TRADERS | 459.33 | 89.61 | 19.51 | 50
9 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PAHARPUR PIPED WATER SUPPLY SCHEME , ZONE-II, TW No I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000131/2023-2024 | 811/NMD | 20/07/2023 | 01/09/2025 | M/S RATAN KUMAR DASGUPTA AND CO. | 21.52 | 0 | 0 | 60
10 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Balance Work of Distribution System for Paharpur Zone - II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000052/2024-2025 | 945/JD | 07/08/2024 | 04/04/2025 | PRIYABRATA KARMAKAR | 24.12 | 0 | 0 | 95
11 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001001/2024-2025 | 22/NMD | 06/01/2025 | 05/02/2025 | SUMON ELECTRICAL | 12.23 | 0 | 0 | 0
12 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
13 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME | SM/16779 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 1200.58 | 92.11 | 7.67