## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | HAIHAIPATHAR PWSS | SM/16852 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1085/JD | 24/08/2023 | 24/08/2023 | Resource Division | 28.59 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | HAIHAIPATHAR PWSS | SM/16852 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | HAIHAIPATHAR PWSS | SM/16852 | New | Sinking of 2 (Two) Nos Tube Well by ODEX-165 method of drilling and construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement and boundary wall for direct boosting in the command area of Hai Hai Pather PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000435/2024-2025 | 2311./JD | 11/12/2024 | 19/02/2025 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 34.93 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Northern Mechanical | HAIHAIPATHAR PWSS | SM/16852 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for HAIHAIPATHAR PWSS, TW No I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000677/2023-2024 | 1490/NMD | 17/08/2023 | 16/09/2023 | ANIMA ENTERPRISE | 25.32 | 25.32 | 99.99 | 100
5 | JALPAIGURI | Mal | Jalpaiguri Division | HAIHAIPATHAR PWSS | SM/16852 | New | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 2022/JD | 09/01/2024 | 09/01/2024 | Resource Division | 14.2 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | HAIHAIPATHAR PWSS | SM/16852 | New | Infrastructure Cost for HAI HAI PATHAR, T/W No. II under MAL CCC [APPLICATION NO. 100000092012 ; Reference ID :860283912] |  |  | BILL/01718/2023-2024 | BP/23-24/251 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.17 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | HAIHAIPATHAR PWSS | SM/16852 | New | New Service Connection Charge for HAI HAI PATHAR, T/W No. II under MAL CCC [APPLICATION NO. 4003255985 ; Reference ID :403097549] |  |  | BILL/01717/2023-2024 | BP/23-24/250 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | HAIHAIPATHAR PWSS | SM/16852 | New | New Service Connection Charge for HAI HAI PATHAR, T/W No. I under MAL CCC [APPLICATION NO. 4003255959 ; Reference ID :403097548] |  |  | BILL/01719/2023-2024 | BP/23-24/252 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | HAIHAIPATHAR PWSS | SM/16852 | New | Additional Quotation for Infrastructure development cost for new service connection at Hai Hai Pather, TW NO-II, MAL CCC APPLICATION NO. 100000103229 Reference ID : 860295639 |  |  | BILL/00214/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.78 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | HAIHAIPATHAR PWSS | SM/16852 | New | Infrastructure Cost for HAI HAI PATHAR, T/W No. I under MAL CCC [APPLICATION NO. 100000091999 ; Reference ID :860283909] |  |  | BILL/01720/2023-2024 | BP/23-24/253 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.11 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | HAIHAIPATHAR PWSS | SM/16852 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 13/01/2025 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Jalpaiguri Division | HAIHAIPATHAR PWSS | SM/16852 | New | Construction of different components of HAIHAIPATHAR PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000048/2023-2024 | 454/JD. | 08/06/2023 | 18/09/2026 | M/S R.N. TRADERS | 444.76 | 221.18 | 49.73 | 75
13 | JALPAIGURI | Mal | Jalpaiguri Division | HAIHAIPATHAR PWSS | SM/16852 | New | Railway track crossing of pipeline at Hai Hai pathor , Mal block, Jalpaiguri. |  |  | BILL/00299/2026-2027 |  | 03/06/2026 | 03/06/2026 | NORTHEAST FRONTIER RAILWAY (IR-RBCS) | 2.47 | 0 | 0 | 0
Total | [13 empty] | 593.3 | 246.49 | 41.55