## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS | SM/16937 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000171/2023-2024 | 1213/NMD | 26/07/2023 | 25/08/2023 | MAA ENTERPRISES | 11.18 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS | SM/16937 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 1055/JD | 24/08/2023 | 24/08/2023 | Resource Division | 3.99 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS | SM/16937 | Augmentation | Rejuvenation work for Pump House & Additional Backwash line for Uttar Bhuskadanga Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000683/2023-2024 | 155/RWS | 15/02/2024 | 16/03/2024 | MRINMOY KANTI DUTTA | 6.13 | 6.01 | 98.01 | 100
4 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS | SM/16937 | Augmentation | New Service Connection Charge for UTTAR BHUSKADANGA(REJU), T/W-III under MAYNAGURI CCC APPLICATION NO. 4003401398 Reference ID : 403211999 |  |  | BILL/00287/2024-2025 | BP/24-25/36 | 14/05/2024 | 14/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.97 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS | SM/16937 | Augmentation | Laying Additional pipeline to improve the water distribution network for Uttar Bhuskadanga Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000702/2024-2025 | 631/JD | 28/03/2025 | 01/11/2025 | MRINMOY KANTI DUTTA | 23.85 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS | SM/16937 | Augmentation | Construction of different components for Rejuvenation of Uttar Bhuskadanga & Gartali Jalpesh PWSS i.e. TW, Pump House, IEP, Rising Main etc. i.c.w. Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000121/2023-2024 | 401/A/JD | 06/06/2023 | 17/02/2025 | KAMALESH SEN | 42.76 | 30.84 | 72.13 | 100
Total | [13 empty] | 98.88 | 36.85 | 37.27