## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | SM/17181 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GATIA TEA GARDEN PWSS, TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000851/2023-2024 | 1803/NMD | 31/10/2023 | 30/11/2023 | SANJIB SAHA | 20.9 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | SM/17181 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1060/JD | 24/08/2023 | 24/08/2023 | Resource Division | 3.73 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | SM/17181 | Augmentation | Sinking of One No Big Dia Tube Well by Modified DTH - ODEX method for 3rd tube well site at Rejuvenation of Gatia Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2025-2026 | 2154/JD | 17/10/2025 | 01/11/2025 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 16.63 | 0 | 0 | 100
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | SM/17181 | Augmentation | INSTALLATION OF 1 NO 25 KVA DTR FOR NSC AT GATIA TG TW-III APPLICATION NO.100000133016 Reference ID :860329546 |  |  | BILL/02975/2024-2025 | 86/W/25-26 | 13/08/2025 | 13/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.33 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme | SM/17181 | Augmentation | "New Service Connection Charge for GATIA TEA GARDEN TW-III " APPLICATION NO.4003610362 Reference ID : 403365416 |  |  | BILL/02974/2024-2025 | 86/W/25-26 | 13/08/2025 | 13/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
Total | [13 empty] | 44.23 | 0 | 0