## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AIBHIL PWSS, TW NO III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000352/2023-2024 | 1313/NMD | 04/08/2023 | 25/04/2025 | UTTAM PAUL | 24.24 | 20.02 | 82.58 | 90
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000211/2023-2024 | 2073/JD | 10/01/2024 | 10/01/2024 | Resource Division | 5.79 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | Infrastructure Cost for AIBHEEL TG, T/W No. IV, under METELLI CCC [APPLICATION NO. 100000095978 ; Reference ID : 860287638] |  |  | BILL/01734/2023-2024 | BP/23-24/255 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.4 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | Infrastructure Cost for AIBHEEL TG, T/W No. III, under METELLI CCC [APPLICATION NO. 100000095977 ; Reference ID : 860287637] |  |  | BILL/01736/2023-2024 | BP/23-24/257 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | New Service Connection Charge for AIBHEEL TG, T/W No. III, under METELLI CCC [APPLICATION NO. 4003293341 ; Reference ID : 403125586] |  |  | BILL/01735/2023-2024 | BP/23-24/256 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | New Service Connection Charge for AIBHEEL TG, T/W No. IV, under METELLI CCC [APPLICATION NO. 4003293345 ; Reference ID : 403125584] |  |  | BILL/01733/2023-2024 | BP/23-24/254 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
Total | [13 empty] | 44.8 | 20.02 | 44.69