## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AIBHIL PWSS, TW NO III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000352/2023-2024 | 1313/NMD | 04/08/2023 | 25/04/2025 | UTTAM PAUL | 24.24 | 0 | 0 | 90
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000211/2023-2024 | 2073/JD | 10/01/2024 | 10/01/2024 | Resource Division | 5.79 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | Infrastructure Cost for AIBHEEL TG, T/W No. IV, under METELLI CCC [APPLICATION NO. 100000095978 ; Reference ID : 860287638] |  |  | BILL/01734/2023-2024 | BP/23-24/255 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.4 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | Infrastructure Cost for AIBHEEL TG, T/W No. III, under METELLI CCC [APPLICATION NO. 100000095977 ; Reference ID : 860287637] |  |  | BILL/01736/2023-2024 | BP/23-24/257 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | New Service Connection Charge for AIBHEEL TG, T/W No. III, under METELLI CCC [APPLICATION NO. 4003293341 ; Reference ID : 403125586] |  |  | BILL/01735/2023-2024 | BP/23-24/256 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | New Service Connection Charge for AIBHEEL TG, T/W No. IV, under METELLI CCC [APPLICATION NO. 4003293345 ; Reference ID : 403125584] |  |  | BILL/01733/2023-2024 | BP/23-24/254 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme | SM/17185 | Augmentation | Sinking 2 Nos Rig Bore TubeWell by ODEX-165 method of dirlling with 2 Nos Pump House (5.4m x 3.6m) and 2 Nos Boundary Wall along with Laying Distribution System including Rising Main with providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Aibhil Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2023-2024 | 366/JD | 26/05/2023 | 16/02/2025 | BARUN KUMAR DUTTA | 96.31 | 0 | 0 | 100
Total | [13 empty] | 141.11 | 0 | 0