## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 1839/JD | 15/12/2023 | 15/12/2023 | Resource Division | 12.71 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | New Service Connection Charge for BARAGHARIA, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003249150, Reference ID : 403091826] |  |  | BILL/01651/2023-2024 | BP/23-24/170 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.88 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | New Service Connection Charge for BARAGHARIA, T/W No. I, under DHUPGURI CCC [APPLICATION NO. 4003248664, Reference ID : 403090252] |  |  | BILL/01650/2023-2024 | BP/23-24/170 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.51 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | Construction of different components of Baragharia PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000026/2023-2024 | 93/JD | 25/04/2023 | 25/04/2026 | SCEC BOENTER KDAS JOINT VENTURE | 431.11 | 0 | 0 | 75
5 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | Providing FHTC in the command area of Baragharia PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000540/2024-2025 | 111/JD | 16/01/2025 | 02/03/2025 | SWAPAN SAHA | 22.58 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | Balance work for Laying Distribution System at Baragharia Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block- Dhupguri under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000179/2025-2026 | 2167/JD | 30/10/2025 | 29/11/2025 | S. DUTTA | 26.33 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. | SM/17649 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA GHARIA PWSS,at TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000417/2023-2024 | 1331/NMD | 08/08/2023 | 17/09/2024 | B.B. CONCERNED | 24.52 | 0 | 0 | 100
Total | [13 empty] | 611.96 | 0 | 0