## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II | SM/18094 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 1057/JD | 24/08/2023 | 24/08/2023 | Resource Division | 4.7 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II | SM/18094 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Maynatali PWSS , in connection with Rejuvenation of Maynatali PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000132/2023-2024 | 405/A/JD | 06/06/2023 | 06/08/2025 | ABHIJIT SARKAR | 47.88 | 0 | 0 | 25
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II | SM/18094 | Augmentation | Providing FHTC and Installation of Sluice Valve at different strategic point in connection with JJM of Mainatali Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000591/2024-2025 | 466/JD | 11/03/2025 | 31/03/2026 | ARUP SARKAR | 24.16 | 0 | 0 | 0
Total | [13 empty] | 76.74 | 0 | 0