## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1090/JD | 24/08/2023 | 24/08/2023 | Resource Division | 24.92 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 524/JSSD | 29/01/2024 | 29/07/2024 | APIKUL ALI | 0.88 | 0.54 | 60.94 | 70
3 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Construction of different components of Oodlabari Tea Garden (Zone-I) PWSS i.e. OHR,TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. of North Bengal Circle-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000065/2024-2025 | 936/JD | 07/08/2024 | 03/06/2025 | SUJIT KUMAR SAHA | 183.05 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. | Assistant Engineer | Junior Engineer | ORD/000820/2023-2024 | 525/JSSD | 29/01/2024 | 29/07/2024 | DHIRAJ BISWAS | 0.88 | 0.77 | 87.15 | 0
5 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.07.2024 to 31.08.2024)" | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000091/2024-2025 | 531/JD | 28/06/2024 | 28/08/2024 | GURUKUL INFOTECH | 3.16 | 3.16 | 100 | 100
6 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 2070/JD | 10/01/2024 | 10/01/2024 | Resource Division | 17.24 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 2029/JD | 19/11/2024 | 19/11/2024 | Resource Division | 108.92 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Infrastructure Cost for ODLABARI TEA GARDEN,T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093886, Reference ID : 860285546] |  |  | BILL/01282/2023-2024 | 23-24/160&168 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.88 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month April'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00130/2024-2025 | BP-2024-25-97 | 22/05/2024 | 22/05/2024 | FILL & SMILE | 0.36 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of Fuel bill for the Month of October'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/01036/2024-2025 | BP-2024-25-560 | 20/12/2024 | 20/12/2024 | FILL & SMILE | 0.15 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00980/2024-2025 | BP-2024-25-531 | 13/12/2024 | 13/12/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month March'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00384/2024-2025 | BP-2024-25-269 | 30/07/2024 | 30/07/2024 | FILL & SMILE | 0.19 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00979/2024-2025 | BP-2024-25-533 | 13/12/2024 | 13/12/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | New Service Connection Charge for ODLABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003424001 Reference ID : 403230049 |  |  | BILL/00410/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
15 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | New Service Connection Charge for ODLABARI TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266395, Reference ID : 403105528] |  |  | BILL/01281/2023-2024 | 23-24/160&168 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.91 | 0 | 0 | 0
16 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of fuel (Diesel) for vehicle no. WB-71B-9430 for the month of February-2024 |  |  | BILL/00097/2024-2025 | BP-2024-25-64 | 14/05/2024 | 14/05/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
17 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 76 7338) |  |  | BILL/00969/2024-2025 | BP-2024-25-529 | 13/12/2024 | 13/12/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
18 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of Fuel bill for the Month of April,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00321/2024-2025 | BP-2024-25-183 | 28/06/2024 | 28/06/2024 | FILL & SMILE | 0.29 | 0 | 0 | 0
19 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of Fuel bill for the Month of November'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/01037/2024-2025 | BP-2024-25-561 | 20/12/2024 | 20/12/2024 | FILL & SMILE | 0.15 | 0 | 0 | 0
20 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month March'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00131/2024-2025 | BP-2024-25-98 | 22/05/2024 | 22/05/2024 | FILL & SMILE | 0.28 | 0 | 0 | 0
21 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00932/2024-2025 | BP-2024-25-523 | 29/11/2024 | 29/11/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
22 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 76 7338) |  |  | BILL/00929/2024-2025 | BP-2024-25-522 | 29/11/2024 | 29/11/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
23 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00966/2024-2025 | BP-2024-25-530 | 13/12/2024 | 13/12/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
24 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month January'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00402/2024-2025 | BP-2024-25-240 | 26/07/2024 | 26/07/2024 | FILL & SMILE | 0.19 | 0 | 0 | 0
25 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
26 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Infrastructure development cost for new service connection at ODLABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000109306 Reference ID : 860301266 |  |  | BILL/00409/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.48 | 0 | 0 | 0
27 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Aug'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00965/2024-2025 | BP-2024-25-532 | 13/12/2024 | 13/12/2024 | FILL & SMILE | 0.21 | 0 | 0 | 0
28 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (Petrol) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 71 B 9586) |  |  | BILL/01038/2024-2025 | BP-2024-25-559 | 20/12/2024 | 20/12/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
29 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00873/2024-2025 | BP-2024-25-497 | 07/10/2024 | 07/10/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
30 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of Fuel bill for the Month of March,2024 Vide Vehicle no-WB71B9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00320/2024-2025 | BP-2024-25-182 | 28/06/2024 | 28/06/2024 | FILL & SMILE | 0.14 | 0 | 0 | 0
31 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of Engine oil, Gear Oil and Kool plus Bill for the Month of April,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte |  |  | BILL/00324/2024-2025 | BP-2024-25-181 | 28/06/2024 | 28/06/2024 | FILL & SMILE | 0.07 | 0 | 0 | 0
32 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month July'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00523/2024-2025 | BP-2024-25-294 | 14/08/2024 | 14/08/2024 | FILL & SMILE | 0.21 | 0 | 0 | 0
33 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Construction of different components of Oodlabari Tea Garden (Zone-II) PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 800/JD. | 24/07/2023 | 01/01/2026 | GHANASHYAM SARKAR | 281.55 | 178.49 | 63.39 | 40
34 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for ODLABARI TEA GARDEN PWSS,at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000757/2023-2024 | 1585/NMD | 08/09/2023 | 01/10/2025 | CHOWDHURY AND BASU ENTERPRISE | 42.08 | 23.04 | 54.77 | 68
35 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. | Assistant Engineer | Junior Engineer | ORD/000212/2024-2025 | 137/JSSD | 29/07/2024 | 27/09/2024 | DHIRAJ BISWAS | 0.88 | 0.44 | 50 | 50
36 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte.(with valid Taxi permit) for supervision and different works at different blocks under Jal Jeevan Mission. Period from 01/08/2024 to 31/01/2025. | Assistant Engineer | Junior Engineer | ORD/000093/2024-2025 | 125/JSSD | 18/07/2024 | 18/01/2025 | APIKUL ALI | 0.88 | 1.29 | 146.04 | 0
37 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st August 2024 to 31st January 2025) | Assistant Engineer | Junior Engineer | ORD/000112/2024-2025 | 142/1/JSSD | 29/07/2024 | 29/01/2025 | APIKUL ALI | 0.88 | 0.29 | 32.76 | 0
38 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM From 01.09.2024 to 28.02.2025 (Vehicle No.: - WB 76 9978) | Assistant Engineer | Junior Engineer | ORD/000159/2024-2025 | 206/JSSD | 30/08/2024 | 28/02/2025 | APIKUL ALI | 0.88 | 2.1 | 237.54 | 0
39 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Continuation of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. (Vehicle No-WB 71B 9586) w.e.f. 1.02.2025-31.07.2025. | Assistant Engineer | Junior Engineer | ORD/000703/2024-2025 | 434/JSSD | 31/01/2025 | 31/07/2025 | DHIRAJ BISWAS | 0.88 | 0.15 | 16.67 | 30
40 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer | Junior Engineer | ORD/000037/2025-2026 | 824/JD | 30/04/2025 | 30/06/2025 | PARAMJYOTI ENTERPRISE | 0.8 | 0.79 | 98.89 | 100
41 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
42 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Continuation work of " Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte.(with valid Taxi permit) for supervision and different works at different blocks under Jal Jeevan Mission". Period from 01.02.2025 to 31.07.2025. (Vichle No. WB 78 3405) | Assistant Engineer | Junior Engineer | ORD/000696/2024-2025 | 418/JSSD | 28/01/2025 | 28/07/2025 | APIKUL ALI | 0.88 | 0.69 | 78.18 | 0
43 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st February 2025 to 31st July 2025) | Assistant Engineer | Junior Engineer | ORD/000697/2024-2025 | 417/JSSD | 28/01/2025 | 28/07/2025 | APIKUL ALI | 0.88 | 0.79 | 89.54 | 0
44 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer | Junior Engineer | ORD/000122/2025-2026 | 1498/JD | 30/06/2025 | 31/07/2025 | PARAMJYOTI ENTERPRISE | 0.4 | 0 | 0 | 100
45 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer | Junior Engineer | ORD/000127/2025-2026 | 1503/JD | 30/06/2025 | 31/07/2025 | PARAMJYOTI ENTERPRISE | 0.4 | 0 | 0 | 100
46 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer | Junior Engineer | ORD/000032/2025-2026 | 819/JD | 30/04/2025 | 30/06/2025 | PARAMJYOTI ENTERPRISE | 0.8 | 0.4 | 49.45 | 100
47 | JALPAIGURI | Mal | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
48 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Construction approach with paver block inside the premises and land ment at HW site & 2nd TW Site of Oodlabari TG (Z-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000178/2025-2026 | 170/JSSD | 24/07/2025 | 23/08/2025 | SUBHANKAR DEY | 6.57 | 0 | 0 | 0
49 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Continuation Order for the Work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.11.2024 to 31.12.2024)" | Assistant Engineer | Junior Engineer | ORD/000558/2024-2025 | 1797/JD | 30/10/2024 | 30/12/2024 | GURUKUL INFOTECH | 3.16 | 0 | 0 | 100
50 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Continuation Order for the Work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.09.2024 to 31.10.2024)" | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000486/2024-2025 | 1215/JD | 28/08/2024 | 28/10/2024 | GURUKUL INFOTECH | 3.16 | 0 | 0 | 100
51 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 11/12/2025 | GURUKUL INFOTECH | 4.83 | 0 | 0 | 100
52 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Tea Garden Water Supply Scheme of Mal, Matiali, Nagrakata Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000157/2024-2025 | 270/JSSD | 25/09/2024 | 24/11/2024 | GURUKUL INFOTECH | 3.16 | 0 | 0 | 100
53 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | FACELIFTING AND INTERIOR FURNINSHING WORKS AT FIRST FLOOR TOILET, SURVEY J. E. ROOM AND JUNIOR ENGINEER ROOM IN GROUND FLOOR UNDER JALPAIGURI DIVISION, P.H.E. DTE. | Assistant Engineer | Junior Engineer 2 | ORD/000699/2024-2025 | 364/JD | 25/02/2025 | 27/03/2025 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 16.07 | 0 | 0 | 100
54 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Design, Fabricating, fitting, Fixing and Erecting of Display Board including Vinyl Pasting (1800mm x 1200mm Size) using Logo and Tag Line of Jal Jeevan Mission (JJM) at different work sites of Har Ghar jal (HGJ) villages of Matiali, Nagrakata & Malbazar Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000709/2024-2025 | 490/JSSD | 21/03/2025 | 28/03/2025 | PRIYABRATA KARMAKAR | 0.84 | 0 | 0 | 100
55 | JALPAIGURI | Mal | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18356 | New | Designing, fabrication and erection of Display Board including vinyl pasting ( 0.9 mtr x 0.6 mtr) for demarcation of land at different PWSS work sites in connection with JJM at MALBAZAR BLOCK in the district of Jalpaiguri, under Jalpaiguri Division , P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000048/2025-2026 | 80/JSSD | 30/05/2025 | 29/06/2025 | GURUKUL INFOTECH | 3.66 | 0 | 0 | 100
Total | [13 empty] | 1256.76 | 212.92 | 16.94