## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 1373/JD | 27/09/2023 | 27/09/2023 | Resource Division | 39.87 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 524/JSSD | 29/01/2024 | 29/07/2024 | APIKUL ALI | 0.88 | 0.56 | 63.85 | 70
3 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. | Assistant Engineer | Junior Engineer | ORD/000820/2023-2024 | 525/JSSD | 29/01/2024 | 29/07/2024 | DHIRAJ BISWAS | 0.88 | 0.59 | 66.47 | 0
5 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 2026/JD | 09/01/2024 | 09/01/2024 | Resource Division | 20.96 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-II,ZONE-II under ODLABARI CCC, [APPLICATION NO. 4003344833, Reference ID : 403166837] |  |  | BILL/02164/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Supply of Fuel bill for the Month of August'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/01032/2024-2025 | BP-2024-25-563 | 20/12/2024 | 20/12/2024 | FILL & SMILE | 0.24 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-II,ZONE-II under ODLABARI CCC, [APPLICATION NO. 100000101170, Reference ID : 860293440] |  |  | BILL/02167/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.67 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Supply of Fuel bill for the Month of JuLY,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00756/2024-2025 | BP-2024-25-416 | 01/10/2024 | 01/10/2024 | FILL & SMILE | 0.21 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | New Service Connection Charge for NEW GLENCO TG, T/W No. I, ZONE-I, under MAL CCC [APPLICATION NO. 4003299833 , Reference ID : 403130048] |  |  | BILL/01797/2023-2024 | BP/23-24/266 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Supply of Fuel bill for the Month of June,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00758/2024-2025 | BP-2024-25-418 | 01/10/2024 | 01/10/2024 | FILL & SMILE | 0.17 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Infrastructure Cost for NEW GLENCO TG, T/W No. II, ZONE-I, under MAL CCC [APPLICATION NO. 100000096849 , Reference ID : 860287699] |  |  | BILL/01800/2023-2024 | BP/23-24/269 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.91 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-I,ZONE-II under ODLABARI CCC, [APPLICATION NO. 4003344844, Reference ID : 403166840] |  |  | BILL/02166/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
15 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-I,ZONE-II under ODLABARI CCC, [APPLICATION NO. 100000101049, Reference ID : 860293439] |  |  | BILL/02165/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.92 | 0 | 0 | 0
16 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Infrastructure Cost for NEW GLENCO TG, T/W No. I, ZONE-I, under MAL CCC [APPLICATION NO. 100000096848 , Reference ID : 860287698] |  |  | BILL/01798/2023-2024 | BP/23-24/267 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0 | 0
17 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | New Service Connection Charge for NEW GLENCO TG, T/W No. II, ZONE-I, under MAL CCC [APPLICATION NO. 4003299838 , Reference ID : 403130049] |  |  | BILL/01799/2023-2024 | BP/23-24/268 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
18 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Construction of different components of New Clenco T.G. (P) (Zone-I & II) PWSS i.e. TW, Pump Housese,Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000159/2023-2024 | 798/JD. | 24/07/2023 | 16/03/2025 | MD HAKIMUDDIN | 554.35 | 438.04 | 79.02 | 100
19 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEW CALENCO TG PWSS, ZONE I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000758/2023-2024 | 1586/NMD | 08/09/2023 | 01/10/2025 | ANUP BASU | 52.66 | 23.47 | 44.56 | 70
20 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including construction of Hume Pipe Culvert at New Clenco Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000225/2024-2025 | 1571/JD | 04/10/2024 | 05/06/2025 | MD HAKIMUDDIN | 88.52 | 0 | 0 | 80
21 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. | Assistant Engineer | Junior Engineer | ORD/000212/2024-2025 | 137/JSSD | 29/07/2024 | 27/09/2024 | DHIRAJ BISWAS | 0.88 | 0.44 | 50 | 50
22 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st August 2024 to 31st January 2025) | Assistant Engineer | Junior Engineer | ORD/000112/2024-2025 | 142/1/JSSD | 29/07/2024 | 29/01/2025 | APIKUL ALI | 0.88 | 0.47 | 52.98 | 0
23 | JALPAIGURI | Mal | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Sinking of 3 (Three) Nos Tube Well by ODEX-165 method of drilling and construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement and boundary wall for direct boosting in the command area of New Clenco TG PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000484/2024-2025 | 2432/JD | 24/12/2024 | 01/01/2026 | MD HAKIMUDDIN | 53.54 | 0 | 0 | 100
24 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 13/01/2025 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
25 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001005/2024-2025 | 25/NMD | 06/01/2025 | 05/02/2025 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0 | 0
26 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
27 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
28 | JALPAIGURI | Mal | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME | SM/18357 | New | Additional Works in connection with Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEW CALENCO TG PWSS, ZONE I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001414/2024-2025 | 690/HQ/NMD | 28/02/2025 | 07/03/2025 | ANUP BASU | 0.91 | 0 | 0 | 0
Total | [13 empty] | 1417.76 | 463.56 | 32.7