## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 148/JD | 28/04/2023 | 28/04/2023 | Resource Division | 76.45 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 2071/JD | 10/01/2024 | 10/01/2024 | Resource Division | 22.22 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Infrastructure development cost for new service connection at CHENGMARIHAT, ZONE-II,TW NO-I, KRANTI CCC APPLICATION NO. 100000105736 Reference ID : 860297936 |  |  | BILL/00243/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.88 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Infrastructure development cost for new service connection at CHENGMARIHAT, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 100000105710 Reference ID : 860298010 |  |  | BILL/00241/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.1 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | New Service Connection Charge for CHENGMARIHAT, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 4003391522 Reference ID : 403203856 |  |  | BILL/00240/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Infrastructure development cost for new service connection at CHENGMARIHAT, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 100000105737 Reference ID : 860297937 |  |  | BILL/00245/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.44 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | New Service Connection Charge for CHENGMARIHAT, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 4003391518 Reference ID : 403203858 |  |  | BILL/00244/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | New Service Connection Charge for CHENGMARIHAT, ZONE-II,TW NO-I, KRANTI CCC APPLICATION NO. 4003391511 Reference ID : 403203859 |  |  | BILL/00242/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Construction of different components of changmarihat Zone-I PWSS i.e TW, Pump House , Water distribution Network , OHR , Boundary wall , RISING MAIN , FHTC etc . In connection with Jal Jeevan Mission at Block kranti under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 849/JD. | 28/07/2023 | 24/06/2026 | S & P ENTERPRISE | 398.61 | 0 | 0 | 25
11 | JALPAIGURI | Mal | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Construction of different components of Changmarihat Zone-II PWSS i.e. TW, Pump Houses,Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 848/JD. | 28/07/2023 | 24/06/2026 | S & P ENTERPRISE | 367.87 | 0 | 0 | 65
12 | JALPAIGURI | Mal | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Construction of different components of Changmarihat Zone-III PWSS i.e. TW, Pump Houses,Water distribution Network, OHR, Boundary Wall, RISING MAIN, FHTC etc. In connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000176/2023-2024 | 847/JD | 28/07/2023 | 24/06/2026 | S & P ENTERPRISE | 234.9 | 0 | 0 | 10
13 | JALPAIGURI | Mal | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHENGMARIHAT PWSS, TW no I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000419/2023-2024 | 1333/NMD | 08/08/2023 | 01/04/2025 | ORIENTAL ENGINEERING CO. | 38.65 | 0 | 0 | 100
14 | JALPAIGURI | Mal | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME | SM/18358 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
Total | [13 empty] | 1324.17 | 0 | 0