## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Construction of different components of Basusuba Zone- II PWSS i.e . TW, Pump House, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division , P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000181/2023-2024 | 851/JD | 28/07/2023 | 24/01/2024 | R.S CONSTRUCTION | 303.82 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 1083/JD | 24/08/2023 | 24/08/2023 | Resource Division | 60.79 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
4 | JALPAIGURI | Mal | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 2075/JD | 10/01/2024 | 10/01/2024 | Resource Division | 17.38 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 03/04/2024 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Infrastructure development cost for new service connection at BASUSUBA, ZONE-I,TW NO-II, KRANTI CCC APPLICATION NO. 100000105734 Reference ID : 860297934 |  |  | BILL/00237/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.29 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | New Service Connection Charge for BASUSUBA, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 4003391439 Reference ID : 403203861 |  |  | BILL/00234/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | New Service Connection Charge for BASUSUBA, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 4003391480 Reference ID : 403203860 |  |  | BILL/00238/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Infrastructure development cost for new service connection at BASUSUBA, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 100000105733 Reference ID : 860297933 |  |  | BILL/00235/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.19 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Infrastructure development cost for new service connection at BASUSUBA, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 100000105735 Reference ID : 860297935 |  |  | BILL/00239/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.72 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | New Service Connection Charge for BASUSUBA, ZONE-I,TW NO-II, KRANTI CCC APPLICATION NO. 4003391463 Reference ID : 403203857 |  |  | BILL/00236/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
12 | JALPAIGURI | Mal | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Construction of different components of Basusuba Zone-III PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. In connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000180/2023-2024 | 846/JD | 28/07/2023 | 01/09/2026 | R.S CONSTRUCTION | 368.89 | 144.41 | 39.15 | 40
13 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BASUSUBA PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000446/2023-2024 | 1385/NMD | 09/08/2023 | 08/09/2023 | M/S RATAN KUMAR DASGUPTA AND CO. | 40.19 | 0 | 0 | 100
14 | JALPAIGURI | Mal | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Construction of different components of Basusuba (Zone-I) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000179/2023-2024 | 850/JD. | 28/07/2023 | 01/09/2026 | R.S CONSTRUCTION | 200.42 | 67.6 | 33.73 | 37
15 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
16 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001008/2024-2025 | 28/NMD | 06/01/2025 | 05/02/2025 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0 | 0
17 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | Infrastructure development cost for new service connection at BASUSUBA, ZONE-III,TW NO-II, KRANTI CCC APPLICATION NO. 100000126895 Reference ID : 860321655 |  |  | BILL/02189/2024-2025 | BP/24-25/251 | 05/02/2025 | 05/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.89 | 0 | 0 | 0
18 | JALPAIGURI | Mal | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME | SM/18359 | New | New Service Connection Charge for BASUSUBA, ZONE-III,TW NO-II, KRANTI CCC APPLICATION NO. 4003562990 Reference ID : 403328662 |  |  | BILL/02188/2024-2025 | BP/24-25/251 | 05/02/2025 | 05/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
Total | [13 empty] | 1234.9 | 212.01 | 17.17