## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 1079/JD | 24/08/2023 | 24/08/2023 | Resource Division | 42.92 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATKATA PWSS ZONE-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000464/2023-2024 | 1440/NMD | 10/08/2023 | 09/09/2023 | SUMON ELECTRICAL | 36.33 | 29.21 | 80.38 | 70
3 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | Construction of different components of Patkata Zone- II Piped Water Supply Scheme i.e TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000445/2023-2024 | 1707/JD | 04/12/2023 | 10/03/2025 | M/S KAMAK ENGINEERS AND CO. | 650.27 | 215.91 | 33.2 | 65
4 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-II)of PATKATA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. |  | Junior Engineer | ORD/001704/2023-2024 | 437/SMSD | 28/03/2024 | 04/04/2024 | M/S PALIDEB ENGINEERING WORKS | 0.73 | 0 | 0 | 0
5 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 2000/JD | 08/01/2024 | 08/01/2024 | Resource Division | 26.02 | 0 | 0 | 0
6 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | New Service Connection Charge for PATKATA, ZONE-II, T/W-II under UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003341677 Reference ID : 403172273 |  |  | BILL/00309/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.2 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | New Service Connection Charge for PATKATA, ZONE-II, T/W-III under UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003365627 Reference ID : 403187095 |  |  | BILL/00308/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.9 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | New Service Connection Charge for PATKATA, ZONE-II, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341680, Reference ID : 403172795] |  |  | BILL/02148/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.12 | 0 | 0 | 0
9 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Patkata Zone-II PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000549/2024-2025 | 114/JD | 16/01/2025 | 25/02/2025 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 23.77 | 0 | 0 | 0
10 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | Distribution System and Functional Household Tap Connection (FHTC) for Patkata Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000024/2024-2025 | 741/JD | 26/07/2024 | 01/04/2026 | PRADIP SAHA | 152.08 | 0 | 0 | 60
11 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
12 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PATKATA ZONE - II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000108/2025-2026 | 486/RWS | 29/05/2025 | 28/06/2025 | EDIFICE ENTERPRISE | 8.05 | 0 | 0 | 0
13 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME | SM/18360 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 1556.64 | 245.11 | 15.75