## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Construction of different components of Chapgar (Zone-I & II) PWSS i.e. TW, Pump Houses, Water distribution Network , OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block -Maynaguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000264/2023-2024 | 944/JD | 08/08/2023 | 04/02/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 488 | 89.09 | 18.26 | 34
2 | JALPAIGURI | Maynaguri | Northern Mechanical | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHAPGAR PWSS, Zone-I,II at TW no I & II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000611/2023-2024 | 1343/NMD | 08/08/2023 | 01/11/2026 | SUNRISE ENGINEERING CORPORATION | 43.76 | 0 | 0 | 50
3 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Continuation Work order for Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R. W.S Sub-Division P.HE. Dte. for 6 month (Period from 01/08/2024 to 31/01/2025) | Assistant Engineer | Junior Engineer | ORD/000054/2024-2025 | 709/RWS | 31/07/2024 | 31/01/2025 | ASHIM SARKAR | 0.88 | 0.88 | 100 | 0
4 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Facelifting and Interior furnishing works for Junior Engineer Room-2 and Estimating Section under Jal;paiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000556/2023-2024 | 502/JSSD | 02/01/2024 | 16/02/2024 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.66 | 9.5 | 98.35 | 100
5 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Facelifting and Interior furishing works for Junior Engineer Room-1 and DPMU Room under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000555/2023-2024 | 501/JSSD | 02/01/2024 | 16/02/2024 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.65 | 8.58 | 88.9 | 100
6 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-C of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 985/JD | 14/08/2024 | 29/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 4.63 | 0 | 0 | 100
7 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Material Requisition To Resource Division |  |  | RTOR000200/2023-2024 | 2061/JD | 10/01/2024 | 10/01/2024 | Resource Division | 9.79 | 0 | 0 | 0
8 | JALPAIGURI | Maynaguri | Northern Mechanical | Chapgar Piped Water Supply Scheme. | SM/18492 | New | New Service Connection Charge for CHAPGAR, ZONE-I,T/W-II under MAYNAGURI CCC APPLICATION NO. 4003379456 Reference ID : 403196953 |  |  | BILL/00205/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0 | 0
9 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00869/2024-2025 | BP-2024-25-495 | 07/10/2024 | 07/10/2024 | FILL & SMILE | 0.02 | 0 | 0 | 0
10 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of August 2024 |  |  | BILL/00650/2024-2025 | BP-2024-25-363 | 13/09/2024 | 13/09/2024 | FILL & SMILE | 0.21 | 0 | 0 | 0
11 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of April 2024 |  |  | BILL/00398/2024-2025 | BP-2024-25-233 | 18/07/2024 | 18/07/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
12 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00934/2024-2025 | BP-2024-25-519 | 25/11/2024 | 25/11/2024 | FILL & SMILE | 0.02 | 0 | 0 | 0
13 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of October 2024 |  |  | BILL/00935/2024-2025 | BP-2024-25-520 | 25/11/2024 | 25/11/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
14 | JALPAIGURI | Maynaguri | Northern Mechanical | Chapgar Piped Water Supply Scheme. | SM/18492 | New | New Service Connection Charge for CHAPGAR, ZONE-I,T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376095 Reference ID : 403191643 |  |  | BILL/00151/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.54 | 0 | 0 | 0
15 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 03/04/2024 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
16 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of September 2024 |  |  | BILL/00868/2024-2025 | BP-2024-25-494 | 07/10/2024 | 07/10/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
17 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00651/2024-2025 | BP-2024-25-362 | 13/09/2024 | 13/09/2024 | FILL & SMILE | 0.02 | 0 | 0 | 0
18 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00399/2024-2025 | BP-2024-25-270 | 30/07/2024 | 30/07/2024 | FILL & SMILE | 0.02 | 0 | 0 | 0
19 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of June 2024 |  |  | BILL/00397/2024-2025 | BP-2024-25-232 | 18/07/2024 | 18/07/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
20 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Material Requisition To Resource Division |  |  | RTOR000003/2025-2026 | 806/JD | 29/04/2025 | 29/04/2025 | Resource Division | 24.62 | 0 | 0 | 0
21 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Material Requisition To Resource Division |  |  | RTOR000110/2024-2025 | 474/JD | 11/03/2025 | 11/03/2025 | Resource Division | 60.26 | 0 | 0 | 0
22 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of December 2024 |  |  | BILL/01088/2024-2025 | BP-2024-25-590 | 17/01/2025 | 17/01/2025 | FILL & SMILE | 0.23 | 0 | 0 | 0
23 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/01087/2024-2025 | BP-2024-25-591 | 17/01/2025 | 17/01/2025 | FILL & SMILE | 0.02 | 0 | 0 | 0
24 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply mobil to vehicle no WB 71 A 5774 for January 2025 |  |  | BILL/01237/2024-2025 | BP-2024-25-668 | 27/03/2025 | 27/03/2025 | FILL & SMILE | 0.02 | 0 | 0 | 0
25 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. | SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of January 2025 |  |  | BILL/01238/2024-2025 | BP-2024-25-669 | 27/03/2025 | 27/03/2025 | FILL & SMILE | 0.23 | 0 | 0 | 0
Total | [13 empty] | 704.58 | 108.05 | 15.34