## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Construction of different components of Nowapara PWSS i.e. TW, Pump Houses, Water distribution Network , OHR, RISING MAIN , FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Divison , P.H.E Dte. |  |  | ORD/000444/2023-2024 | 1775/JD | 08/12/2023 | 05/06/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 686.37 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1106/JD | 24/08/2023 | 24/08/2023 | Resource Division | 28.96 | 0 | 0 | 0
3 | JALPAIGURI | Rajganj | Northern Mechanical | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NOWAPARA PWSS, TW no I , II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000658/2023-2024 | 1472/NMD | 17/08/2023 | 16/09/2023 | M/S RATAN KUMAR DASGUPTA AND CO. | 32.15 | 0 | 0 | 0
4 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Material Requisition To Resource Division |  |  | RTOR000188/2023-2024 | 2033/JD | 09/01/2024 | 09/01/2024 | Resource Division | 22.38 | 0 | 0 | 0
5 | JALPAIGURI | Rajganj | Northern Mechanical | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | New Service Connection Charge for NAWAPARA, TW NO-I, NJP GB CCC APPLICATION NO. 4003354727 Reference ID : 403174711 |  |  | BILL/00433/2024-2025 | BP/24-25/87 | 18/06/2024 | 18/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0 | 0
6 | JALPAIGURI | Rajganj | Northern Mechanical | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
7 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000602/2024-2025 | 271/JD | 07/02/2025 | 22/02/2025 | SAPTASWA SARKAR | 13.75 | 0 | 0 | 100
8 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.06.2024 to 30.11.2024)". | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000005/2024-2025 | 347/JD | 31/05/2024 | 30/11/2024 | RUPA PRASAD | 0.88 | 0 | 0 | 100
9 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000035/2025-2026 | 822/JD | 30/04/2025 | 30/06/2025 | AJIJUL HAQUE | 0.8 | 0 | 0 | 0
10 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000034/2025-2026 | 821/JD | 30/04/2025 | 30/06/2025 | MD AMIRUL ISLAM | 0.8 | 0 | 0 | 0
11 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000125/2025-2026 | 1501/JD | 30/06/2025 | 31/07/2025 | AJIJUL HAQUE | 0.4 | 0 | 0 | 0
12 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Balance Laying Distribution System and Functional Household Tap Connection in connection with Jal Jeevan Mission for Nowapara Piped Water Supply Scheme Block - Rajganj under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000010/2025-2026 | 893/JD | 08/05/2025 | 01/04/2026 | SAHA CONSTRUCTION | 75.34 | 0 | 0 | 0
13 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000124/2025-2026 | 1500/JD | 30/06/2025 | 31/07/2025 | MD AMIRUL ISLAM | 0.4 | 0 | 0 | 0
14 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000198/2025-2026 | 1997/JD | 25/09/2025 | 25/11/2025 | MD AMIRUL ISLAM | 0.8 | 0 | 0 | 0
15 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000471/2025-2026 | 2438/JD | 27/11/2025 | 27/12/2025 | MD AMIRUL ISLAM | 0.4 | 0 | 0 | 0
16 | JALPAIGURI | Rajganj | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME | SM/18503 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000150/2025-2026 | 1731/JD | 31/07/2025 | 30/09/2025 | MD AMIRUL ISLAM | 0.8 | 0 | 0 | 0
Total | [13 empty] | 915.18 | 0 | 0