## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Damdim TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000430/2024-2025 | 2274/JD | 05/12/2024 | 05/03/2025 | PRASENJIT BASAK | 91.26 | 0 | 0 | 0
3 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Estimate for Balance work of Water Distribution Network in Damdim Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000801/2023-2024 | 569/JSSD | 05/03/2024 | 04/04/2024 | PRABIR SHOME | 9.05 | 0 | 0 | 100
4 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 2017/JD | 09/01/2024 | 09/01/2024 | Resource Division | 12.02 | 0 | 0 | 0
5 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Material Requisition To Resource Division |  |  | RTOR000051/2024-2025 | 2071/JD | 25/11/2024 | 25/11/2024 | Resource Division | 38.02 | 0 | 0 | 0
6 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Infrastructure Cost for DAMDIM TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000098645, Reference ID : 860290455] |  |  | BILL/01984/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4 | 0 | 0 | 0
7 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | New Service Connection Charge for DAMDIM TEA GARDEN, T/W No.I, under ODLABARI CCC, [APPLICATION NO. 4003325562, Reference ID : 403151430] |  |  | BILL/01983/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
8 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Infrastructure Cost for DAMDIM TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000098644, Reference ID : 860290454] |  |  | BILL/01986/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.25 | 0 | 0 | 0
9 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | New Service Connection Charge for DAMDIM TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003325572, Reference ID : 403151429] |  |  | BILL/01985/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
10 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
11 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Construction of different components of Damdim Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 1257/JD | 13/09/2023 | 12/05/2025 | PRASENJIT BASAK | 297.11 | 0 | 0 | 40
12 | JALPAIGURI | Mal | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Damdim TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000081/2025-2026 | 100/JSSD | 30/05/2025 | 01/04/2026 | JAYA SARKAR | 6.37 | 0 | 0 | 0
13 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
14 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
15 | JALPAIGURI | Mal | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/18711 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAMDIM TEA GARDEN PWSS, ,TW no I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000465/2023-2024 | 1441/NMD | 10/08/2023 | 01/12/2024 | DILIP MAHATO | 25.34 | 0 | 0 | 100
Total | [13 empty] | 1040.23 | 0 | 0