## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Construction of Boundary Wall, Foot Path, Drain, Pipeline for Washout at HW Site Saptibari Zone-III PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000782/2023-2024 | 2627/JD | 07/03/2024 | 21/04/2024 | SWAPAN SAHA | 23.15 | 0 | 0 | 0
2 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Construction of Boundary Wall, Foot Path, Drain, Pipeline for Washout at HW Site Saptibari Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000777/2023-2024 | 2498/JD | 28/02/2024 | 13/04/2024 | M/S BOSE ENTERPRISE | 22.62 | 0 | 0 | 0
3 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd Tubewell site Saptibari Zone-I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000687/2023-2024 | 151/RWS | 15/02/2024 | 16/03/2024 | DEBABRATA SARKAR | 6.97 | 0 | 0 | 100
4 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd Tubewell site Saptibari Zone-III PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000688/2023-2024 | 150/RWS | 15/02/2024 | 16/03/2024 | SOUVIK SAHA | 7.24 | 0 | 0 | 100
5 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Construction of Boundary Wall, Foot Path, Drain, pipeline for washout at 2nd Tubewell site Saptibari Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000805/2023-2024 | 257/RWS | 07/03/2024 | 06/04/2024 | UCO LABOUR CO-OPERATIVE SOCIETY LTD. | 7.24 | 0 | 0 | 100
6 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 51/JD | 09/04/2024 | 09/04/2024 | Resource Division | 64.27 | 0 | 0 | 0
7 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 2036/JD | 09/01/2024 | 09/01/2024 | Resource Division | 37.59 | 0 | 0 | 0
8 | JALPAIGURI | Maynaguri | Northern Mechanical | Saptibari Piped Water Supply Scheme. | SM/18759 | New | New Service Connection Charge for SAPTIBARI ZONE-I, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003356521 Reference ID : 403175893 |  |  | BILL/00184/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.98 | 0 | 0 | 0
9 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00366/2024-2025 | BP-2024-25-271 | 30/07/2024 | 30/07/2024 | FILL & SMILE | 0.02 | 0 | 0 | 0
10 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of May 2024 |  |  | BILL/00365/2024-2025 | BP-2024-25-191 | 08/07/2024 | 08/07/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
11 | JALPAIGURI | Maynaguri | Northern Mechanical | Saptibari Piped Water Supply Scheme. | SM/18759 | New | New Service Connection Charge for SAPTIBARI, T/W No. II, ZONE-II under BHOTPATTY CCC [APPLICATION NO. 4003305811 ; Reference ID : 403134435] |  |  | BILL/01863/2023-2024 | BP/23-24/292 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.32 | 0 | 0 | 0
12 | JALPAIGURI | Maynaguri | Northern Mechanical | Saptibari Piped Water Supply Scheme. | SM/18759 | New | New Service Connection Charge for SAPTIBARI, T/W No. I, ZONE-II under BHOTPATTY CCC [APPLICATION NO. 4003305806 ; Reference ID : 403134432] |  |  | BILL/01862/2023-2024 | BP/23-24/291 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.26 | 0 | 0 | 0
13 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 03/04/2024 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
14 | JALPAIGURI | Maynaguri | Northern Mechanical | Saptibari Piped Water Supply Scheme. | SM/18759 | New | New Service Connection Charge for SAPTIBARI, T/W No. II, ZONE-III under BHOTPATTY CCC [APPLICATION NO. 4003305829 ; Reference ID : 403134442] |  |  | BILL/01865/2023-2024 | BP/23-24/295 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.59 | 0 | 0 | 0
15 | JALPAIGURI | Maynaguri | Northern Mechanical | Saptibari Piped Water Supply Scheme. | SM/18759 | New | New Service Connection Charge for SAPTIBARI, T/W No. I, ZONE-III under BHOTPATTY CCC [APPLICATION NO. 4003305819 ; Reference ID : 403134444] |  |  | BILL/01864/2023-2024 | BP/23-24/293 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.07 | 0 | 0 | 0
16 | JALPAIGURI | Maynaguri | Northern Mechanical | Saptibari Piped Water Supply Scheme. | SM/18759 | New | New Service Connection Charge for SAPTIBARI ZONE-I, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003356527 Reference ID : 403175900 |  |  | BILL/00185/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.3 | 0 | 0 | 0
17 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Construction of different components of Saptibari (Zone-II) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000326/2023-2024 | 1351/JD | 26/09/2023 | 01/04/2026 | SCEC BOENTER KDAS JOINT VENTURE | 445.3 | 0 | 0 | 90
18 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Construction of different components of Saptibari (Zone-I) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 1350/JD | 26/09/2023 | 01/04/2026 | SCEC BOENTER KDAS JOINT VENTURE | 571.97 | 0 | 0 | 90
19 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Construction of different components of Saptibari (Zone-III) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000327/2023-2024 | 1352/JD | 26/09/2023 | 01/04/2026 | SCEC BOENTER KDAS JOINT VENTURE | 432.29 | 0 | 0 | 79
20 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Balance Work of Distribution System for Saptibari Zone- II Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000071/2024-2025 | 987/JD | 14/08/2024 | 09/08/2025 | MONOJ GHOSH | 59.77 | 0 | 0 | 85
21 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Balance Work of Distribution System for Saptibari Zone- III Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000188/2024-2025 | 1534/JD | 01/10/2024 | 01/06/2025 | KAMALESH SEN | 52.66 | 0 | 0 | 90
22 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Balance Work of Distribution System for Saptibari Zone-I Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000674/2024-2025 | 486/JD | 11/03/2025 | 09/07/2025 | DIPAK KUMAR CHAKRABORTY | 71.83 | 0 | 0 | 0
23 | JALPAIGURI | Maynaguri | Northern Mechanical | Saptibari Piped Water Supply Scheme. | SM/18759 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SAPTIBARI PWSS, ZONE-I,II,III AT TW NO I,II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000738/2023-2024 | 1553/NMD | 04/09/2023 | 01/04/2025 | EASTERN INDIA SALES & SERVICE | 67.81 | 0 | 0 | 100
Total | [13 empty] | 1960.9 | 0 | 0