## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 2063/JD | 10/01/2024 | 10/01/2024 | Resource Division | 43.48 | 0 | 0 | 0
3 | JALPAIGURI | Jalpaiguri | Northern Mechanical | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | New Service Connection Charge for SATKHAMAR, T/W- V, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341726, Reference ID : 403171912] |  |  | BILL/02150/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.46 | 0 | 0 | 0
4 | JALPAIGURI | Jalpaiguri | Northern Mechanical | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | New Service Connection Charge for SATKHAMAR, T/W- VI, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341729, Reference ID : 403172439] |  |  | BILL/02149/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.69 | 0 | 0 | 0
5 | JALPAIGURI | Jalpaiguri | Northern Mechanical | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | New Service Connection Charge for SATKHAMAR, ZONE-I, T/W-I under UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003351968 Reference ID : 403174734 |  |  | BILL/00305/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.49 | 0 | 0 | 0
6 | JALPAIGURI | Jalpaiguri | Northern Mechanical | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | New Service Connection Charge for SATKHAMAR, ZONE-I,T/W-III, under UKILPARA MASKALIBARI CCC APPLICATION NO. 4003341662 Reference ID : 403174732 |  |  | BILL/00160/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.96 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | New Service Connection Charge for SATKHAMAR, ZONE-I,T/W-II, under UKILPARA MASKALIBARI CCC APPLICATION NO. 4003338890 Reference ID : 403162909 |  |  | BILL/00158/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.26 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Supply of Fuel (Petrol) of Vehicle No. WB 49 K 9449 for the Month of August 2024. |  |  | BILL/00648/2024-2025 | BP-2024-25-365 | 13/09/2024 | 13/09/2024 | FILL & SMILE | 0.22 | 0 | 0 | 0
9 | JALPAIGURI | Jalpaiguri | Northern Mechanical | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | New Service Connection Charge for SATKHAMAR, T/W- IV, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341723, Reference ID : 403171803] |  |  | BILL/02151/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
10 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 03/04/2024 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
11 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of September 2024. |  |  | BILL/00851/2024-2025 | BP-2024-25-486 | 07/10/2024 | 07/10/2024 | FILL & SMILE | 0.22 | 0 | 0 | 0
12 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Construction of different components of Satkhamar Zone- II Piped Water Supply Scheme i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000440/2023-2024 | 1705/JD | 04/12/2023 | 02/04/2026 | M/S A.B.G. CONSTRUCTION | 590.4 | 0 | 0 | 90
13 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Construction of Boundary wall, Foot Path, Drain, pipeline for washout at HW site Satkhamar - II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000089/2024-2025 | 1174/JD | 23/08/2024 | 02/04/2026 | M/S A.B.G. CONSTRUCTION | 31.86 | 0 | 0 | 0
14 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Distribution System and Functional Household Tap Connection (FHTC) for Sathkumar Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2024-2025 | 737/JD | 26/07/2024 | 01/01/2026 | ASIM GUPTA | 166.13 | 0 | 0 | 100
15 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Distribution System and Functional Household Tap Connection (FHTC) for Sathkumar Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000027/2024-2025 | 738/JD | 26/07/2024 | 02/04/2026 | ANUP KUNDU CONSTRUCTION CO | 142.74 | 0 | 0 | 95
16 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000101/2024-2025 | 874/JD | 31/07/2024 | 31/01/2025 | SOUMEN GHOSH | 0.88 | 0 | 0 | 0
17 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Construction of Iron Elemination Plant (IEP) including interconnection work and washout line at H/W site in Zone-II Satkhamar PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000529/2024-2025 | 46/JD | 09/01/2025 | 06/09/2025 | M/S M.B. DESIGN | 43.97 | 0 | 0 | 80
18 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Construction of Boundary Wall ,Foot Path,Drain at 2nd site at zone - II of Satkhamar PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000112/2025-2026 | 490/RWS | 29/05/2025 | 28/06/2025 | CHANDAN GHOSH | 5.77 | 0 | 0 | 0
19 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Construction of Boundary Wall ,Foot Path,Drain at 2nd site at zone - I of Satkhamar PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000113/2025-2026 | 491/RWS | 29/05/2025 | 02/04/2026 | SUKES BASU MAJUMDAR | 6.1 | 0 | 0 | 100
20 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Laying Additional Distribution line with providing and installation of Sluice Valve and Specials at Zone-I of Satkhamar Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000170/2025-2026 | 2108/JD | 15/10/2025 | 01/04/2026 | SUKES BASU MAJUMDAR | 32.96 | 0 | 0 | 100
21 | JALPAIGURI | Jalpaiguri | Northern Mechanical | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SATKHAMAR PWSS, ZONE - I (TW NO I, II, III) AND ZONE - II (TW NO I, II, III) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000737/2023-2024 | 1552/NMD | 04/09/2023 | 01/05/2025 | M/S BHOWMICK & CO. | 64.9 | 0 | 0 | 100
22 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. | SM/18760 | New | Construction of different components of Sathkhamar Zone- I Piped Water Suply Scheme i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 1671/JD | 24/11/2023 | 30/04/2025 | SUKES BASU MAJUMDAR | 735.05 | 0 | 0 | 10
Total | [13 empty] | 1981.54 | 0 | 0