## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Singimari Piped Water Supply Scheme. | SM/18761 | New | Construction of different components of Singimari PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC, etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000328/2023-2024 | 1349/JD | 26/09/2023 | 27/03/2025 | M/S R.N. TRADERS | 724.62 | 0 | 0 | 15
2 | JALPAIGURI | Maynaguri | Northern Mechanical | Singimari Piped Water Supply Scheme. | SM/18761 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SINGIMARI PWSS,at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000937/2023-2024 | 1751/NMD | 31/10/2023 | 01/06/2025 | M/S PARITOSH BHOWMICK AND CO. | 32.98 | 0 | 0 | 50
3 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Singimari Piped Water Supply Scheme. | SM/18761 | New | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, Land Development etc. at 2nd TW Site for Singimari PWSS icw JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer |  | ORD/000429/2024-2025 | 1152/RWS | 03/12/2024 | 02/01/2025 | PRABIR SHOME | 9.14 | 0 | 0 | 0
4 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Singimari Piped Water Supply Scheme. | SM/18761 | New | Construction of Boundary Wall Rising Main Interconnection, Pathway, Drain etc. at HW Site for Singimari PWSS icw JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000075/2024-2025 | 1297/JD | 05/09/2024 | 04/11/2024 | KAMAL DAS | 20.16 | 0 | 0 | 0
5 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Singimari Piped Water Supply Scheme. | SM/18761 | New | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 2042/JD | 09/01/2024 | 09/01/2024 | Resource Division | 17.33 | 0 | 0 | 0
6 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Singimari Piped Water Supply Scheme. | SM/18761 | New | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 56/JD | 09/04/2024 | 09/04/2024 | Resource Division | 21.92 | 0 | 0 | 0
7 | JALPAIGURI | Maynaguri | Northern Mechanical | Singimari Piped Water Supply Scheme. | SM/18761 | New | New Service Connection Charge for SINGIMARI, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003376114 Reference ID : 403191660 |  |  | BILL/00149/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.73 | 0 | 0 | 0
8 | JALPAIGURI | Maynaguri | Northern Mechanical | Singimari Piped Water Supply Scheme. | SM/18761 | New | New Service Connection Charge for SINGIMARI, T/W-III under MAYNAGURI CCC APPLICATION NO. 4003376577 Reference ID : 403191663 |  |  | BILL/00156/2024-2025 | BP/24-25/25 | 09/05/2024 | 09/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.21 | 0 | 0 | 0
9 | JALPAIGURI | Maynaguri | Northern Mechanical | Singimari Piped Water Supply Scheme. | SM/18761 | New | New Service Connection Charge for SINGIMARI, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003379454 Reference ID : 403196948 |  |  | BILL/00204/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.38 | 0 | 0 | 0
10 | JALPAIGURI | Maynaguri | Jalpaiguri Division | Singimari Piped Water Supply Scheme. | SM/18761 | New | Balance Laying Distribution System including providing Functional Household Tap Connection in connection with JJM under Singimari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000550/2024-2025 | 127/JD | 16/01/2025 | 17/03/2025 | SWAPAN SAHA | 34.8 | 0 | 0 | 0
Total | [13 empty] | 887.28 | 0 | 0