## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | Dakshin Jharalta Piped Water Supply Scheme. | SM/18835 | New | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 1842/JD | 15/12/2023 | 15/12/2023 | Resource Division | 21.75 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | Dakshin Jharalta Piped Water Supply Scheme. | SM/18835 | New | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 55/JD | 09/04/2024 | 09/04/2024 | Resource Division | 108.57 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Northern Mechanical | Dakshin Jharalta Piped Water Supply Scheme. | SM/18835 | New | New Service Connection Charge for DAKSHIN JHARALTA, T/W No. III, under DHUPGURI CCC [APPLICATION NO. 4003328083 ; Reference ID : 403153545] |  |  | BILL/02017/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.33 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Northern Mechanical | Dakshin Jharalta Piped Water Supply Scheme. | SM/18835 | New | New Service Connection Charge for DAKSHIN JHARALTA, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003328082 , Reference ID : 403153543] |  |  | BILL/01995/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.97 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | Dakshin Jharalta Piped Water Supply Scheme. | SM/18835 | New | New Service Connection Charge for DAKSHIN JHARALTA, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003356729 Reference ID : 403176999 |  |  | BILL/00128/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.35 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | Dakshin Jharalta Piped Water Supply Scheme. | SM/18835 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN JHARALTA PWSS,at TW NO I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000855/2023-2024 | 1805/NMD | 31/10/2023 | 01/10/2025 | PADMA ENGINEERING CO. | 34.35 | 22.16 | 64.51 | 95
7 | JALPAIGURI | Dhupguri | Jalpaiguri Division | Dakshin Jharalta Piped Water Supply Scheme. | SM/18835 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Dhupguri, Rajganj and Balance of Banarhat Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2024-2025 | 940/JD | 07/08/2024 | 06/11/2025 | AKG UDYOG | 25.37 | 0 | 0 | 45
8 | JALPAIGURI | Dhupguri | Jalpaiguri Division | Dakshin Jharalta Piped Water Supply Scheme. | SM/18835 | New | Material Requisition To Resource Division |  |  | RTOR000103/2024-2025 | 512/JD | 13/03/2025 | 13/03/2025 | Resource Division | 30.21 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Jalpaiguri Division | Dakshin Jharalta Piped Water Supply Scheme. | SM/18835 | New | CONSTRUCTION OF DIFFERENT COMPONENTS OF DAKSHIN JHARALTA PWSS i.e, TW, PUMP HOUSES, WATER DISTRIBUTION NETWORK, OHR, RISING MAIN, FHTC etc. IN CONNECTION WITH JAL JEEVAN MISSION AT BLOCK- DHUPGURI UNDER JALPAIGURI DIVISION, P.H.E. DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000378/2023-2024 | 1540/JD | 23/10/2023 | 24/04/2026 | SCEC BOENTER AND KDAS JOINT VENTURE | 864.13 | 286.94 | 33.21 | 70
Total | [13 empty] | 1101.02 | 309.1 | 28.07