## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Northern Mechanical | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SHIKARPUR BHANDARPUR PWSS at TW NO I,II,III (ZONE-I,II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000210/2024-2025 | 1404/NMD | 21/08/2024 | 20/09/2024 | ALPHA ENTERPRISE | 68.61 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Rajganj block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer | Junior Engineer | ORD/000467/2023-2024 | 1292/RWS | 29/11/2023 | 29/12/2023 | B.M CONSTRUCTION | 3.89 | 3.89 | 100 | 100
3 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Motherboard and Power Supply Unit for Office use. |  |  | BILL/00827/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
4 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Toner for Office use. |  |  | BILL/00838/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
5 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Motherboard, RAM and Printer Relay Unit for Office use. |  |  | BILL/00832/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
6 | JALPAIGURI | Rajganj | Northern Mechanical | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | New Service Connection Charge for SHIKARPUR, ZONE-II, TW NO-III, BELAKOBA CCC APPLICATION NO. 4003453990 Reference ID : 403250073 |  |  | BILL/01367/2024-2025 | BP/24-25/237 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.38 | 0 | 0 | 0
7 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of RAM, Logic Board, Pickup Roller and Teflon for Office use. |  |  | BILL/00823/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
8 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Printer Logic Board and Pickup Roller for Office use. |  |  | BILL/00825/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
9 | JALPAIGURI | Rajganj | Northern Mechanical | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | New Service Connection Charge for SHIKARPUR, ZONE-I, TW NO-III, BELAKOBA CCC APPLICATION NO. 4003453987 Reference ID : 403250072 |  |  | BILL/01268/2024-2025 | BP/24-25/204 | 12/09/2024 | 12/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.05 | 0 | 0 | 0
10 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Motherboard, RAM, Pickup Roller and Toner for Office use. |  |  | BILL/00836/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
11 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Printer Power Supply, Teflon for Office use. |  |  | BILL/00826/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
12 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Printer Teflon, Toner for Office use. |  |  | BILL/00820/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
13 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of SSD, Hard Disk and Printer Power Supply Board for Office use. |  |  | BILL/00834/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
14 | JALPAIGURI | Rajganj | Northern Mechanical | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | New Service Connection Charge for SHIKARPUR PWSS, ZONE-II, TW NO. I, under BELAKOBA CCC APPLICATION NO. 4003430829 Reference ID : 403234010 |  |  | BILL/01073/2024-2025 | BP/24-25/167 | 29/08/2024 | 29/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.73 | 0 | 0 | 0
15 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Brother 263 Toner, 88A Toner, 110A Toner, Keyboard and Mouse for Office use. |  |  | BILL/00829/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
16 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Motherboard, Toner and Printer Fuser Unit for Office use. |  |  | BILL/00833/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
17 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Brother Toner and SMPS for Office use. |  |  | BILL/00837/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
18 | JALPAIGURI | Rajganj | Northern Mechanical | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | New Service Connection Charge for SHIKARPUR PWSS, ZONE-I, TW NO. I, under BELAKOBA CCC APPLICATION NO. 4003430831 Reference ID : 403234013 |  |  | BILL/01072/2024-2025 | BP/24-25/167 | 29/08/2024 | 29/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.26 | 0 | 0 | 0
19 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Toner and Mouse for Office use. |  |  | BILL/00819/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.08 | 0 | 0 | 0
20 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of 88A Compatible Toner for Office use. |  |  | BILL/00831/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.07 | 0 | 0 | 0
21 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Motherboard, SSD & Keyboard and Mouse for Office use. |  |  | BILL/00830/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
22 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Logic Board, Power Supply and Teflon for Office use. |  |  | BILL/00839/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
23 | JALPAIGURI | Rajganj | Northern Mechanical | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | New Service Connection Charge for SHIKARPUR, ZONE-II, TW NO-II, BELAKOBA CCC APPLICATION NO. 4003430808 Reference ID : 403234012 |  |  | BILL/01267/2024-2025 | BP/24-25/204 | 12/09/2024 | 12/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.58 | 0 | 0 | 0
24 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Magnetic Relay, Logic Board and Pickup Roller for Office use. |  |  | BILL/00824/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
25 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of SSD, Motherboard, Processor, SMPS and Mouse for Office use. |  |  | BILL/00835/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
26 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Toner, SSD and Ink for Office use. |  |  | BILL/00821/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
27 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Processor, RAM, SMPS and SSD for Office use. |  |  | BILL/00822/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.06 | 0 | 0 | 0
28 | JALPAIGURI | Rajganj | Northern Mechanical | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | New Service Connection Charge for SHIKARPUR PWSS, ZONE-I, TW NO. II, under BELAKOBA CCC APPLICATION NO. 4003430834 Reference ID : 403234011 |  |  | BILL/01071/2024-2025 | BP/24-25/167 | 29/08/2024 | 29/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.36 | 0 | 0 | 0
29 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Logic Board, Magnetic Relay and Teflon for Office use. |  |  | BILL/00840/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
30 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Supply of Toner and Desktop RAM for Office use. |  |  | BILL/00828/2024-2025 | BP-2024-25-500 | 07/10/2024 | 07/10/2024 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
31 | JALPAIGURI | Rajganj | Northern Mechanical | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
32 | JALPAIGURI | Rajganj | Northern Mechanical | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Installation of two tank chlorination system at SHIKARPUR and other adjacent water supply scheme UNDER JJM under RAJGANJ Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/000888/2024-2025 | 80/SMSD | 07/02/2025 | 22/02/2025 | CHOWDHURY AND BASU ENTERPRISE | 1.57 | 0 | 0 | 0
33 | JALPAIGURI | Rajganj | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. | SM/18836 | New | Construction of different components of Shikarpur Bhandarpur Zone - I PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block - RAJGANJ under Jalpaiguri Division, P.H.E.Dte. of North Bengal Circle-I, PHE Dte under JJM Programme. | Assistant Engineer,HQ | Junior Engineer | ORD/000817/2023-2024 | 2623/JD | 07/03/2024 | 01/09/2026 | ASHIT KUMAR SINGHA | 682.9 | 363.2 | 53.18 | 85
Total | [13 empty] | 840.92 | 367.09 | 43.65