## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Construction of different components of Paharpur Zone - I Piped Water Supply Scheme i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2023-2024 | 1820/JD | 14/12/2023 | 01/06/2025 | UNIBRO INFRASERV PRIVATE LIMITED | 616.92 | 141.91 | 23 | 80
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 1081/JD | 24/08/2023 | 24/08/2023 | Resource Division | 40.23 | 0 | 0 | 0
3 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Distribution System and Functional Household Tap Connection (FHTC) for Paharpur Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000026/2024-2025 | 739/JD | 26/07/2024 | 01/04/2026 | GOUTAM DAS | 108.29 | 17.91 | 16.54 | 60
4 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PAHARPUR PIPED WATER SUPPLY SCHEME , ZONE-I, TW No I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001416/2023-2024 | 487/NMD | 12/02/2024 | 02/12/2025 | SUMON ELECTRICAL | 23.55 | 19.16 | 81.38 | 100
5 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 05/10/2024 | GOURAV CONSTRUCTION CO. | 4.93 | 4.9 | 99.29 | 90
6 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 2005/JD | 08/01/2024 | 08/01/2024 | Resource Division | 20.68 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | New Service Connection Charge for PAHARPUR, ZONE-I, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 40033441732, Reference ID : 403172479] |  |  | BILL/02153/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.37 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | New Service Connection Charge for PAHARPUR, ZONE-I, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341737, Reference ID : 403171420] |  |  | BILL/02152/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.18 | 0 | 0 | 0
9 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Paharpur Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000531/2024-2025 | 113/JD | 16/01/2025 | 25/02/2025 | TEESTA CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCITY LIMITED. | 17.91 | 0 | 0 | 100
10 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001001/2024-2025 | 22/NMD | 06/01/2025 | 05/02/2025 | SUMON ELECTRICAL | 12.23 | 0 | 0 | 0
11 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PAHARPUR ZONE - I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000109/2025-2026 | 487/RWS | 29/05/2025 | 28/06/2025 | GURUKUL INFOTECH | 4.32 | 0 | 0 | 0
12 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
13 | JALPAIGURI | Jalpaiguri | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
14 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME | SM/19097 | New | Material Requisition To Resource Division |  |  | RTOR000002/2025-2026 | 805/JD | 29/04/2025 | 29/04/2025 | Resource Division | 6.11 | 0 | 0 | 0
Total | [13 empty] | 1471.96 | 183.88 | 12.49