## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Jalpaiguris District under Jalpaiguri Division. P | SM/19171 | Support-IEC | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000035/2024-2025 | 942/JD | 07/08/2024 | 17/08/2024 | BALARAM GHOSH & SONS | 2.21 | 0 | 0 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Jalpaiguris District under Jalpaiguri Division. P | SM/19171 | Support-IEC | Execution of Special Community Mobilization and Community Ownership Drive through printing & Supply IEC Leaflets & Banner for distribution on FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water, Water Quality issues, water conservation and WASH related issues as per guideline of JJM and preparation of web based Digital (A/V) awareness generation cum training material (Bengali) with voice over showcasing IEC and HRD initiative at Jalpaiguri District under Jalpaiguri Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer,HQ |  | ORD/000144/2025-2026 | 1639/JD | 17/07/2025 | 17/10/2025 | SHOUMMYODIP & CO | 13.33 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Jalpaiguris District under Jalpaiguri Division. P | SM/19171 | Support-IEC | Execution of Special Community Mobilization and Community Ownership Drive through Tableau (Mobile IEC Van), Street Play and Miking on JJM / FHTC; Save Water; Water Conservation, illegal pumping & connection; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Jalpaiguri District under Jalpaiguri Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer,HQ |  | ORD/000143/2025-2026 | 1638/JD | 17/07/2025 | 17/10/2025 | DEBNATH BROTHERS | 26.91 | 0 | 0 | 0
Total | [13 empty] | 42.46 | 0 | 0