## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/19175 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHENGMARI TG AREA PWSS, TW no 1 to 9 in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000869/2023-2024 | 1817/NMD | 01/11/2023 | 01/12/2023 | CONCORD ENGINEERING | 103.77 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/19175 | Augmentation | Construction of Intake Well for Sub-Surface Water Source at River Bed of Diana under Nagrakata Block of Jalpaiguri District i.c.w Chengmari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000740/2023-2024 | 2495/JD | 28/02/2024 | 20/03/2024 | GOUTAM DAS | 37.37 | 37.49 | 100.31 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/19175 | Augmentation | Surveying, Planning, Designing, Construction, Supply and installation and commissioning of surface (River) based water treatment unit to yield 1430 KLD drinking water (Phase-I) on EPC- Turnkey basis for Augmentation of Chengmari Tea Garden Pipe Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000205/2024-2025 | 1590/JD | 23/10/2024 | 11/03/2026 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 936.29 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/19175 | Augmentation | Hydro-Geological survey and investigation and source sustainability for Augmentation of Chengmari Tea Garden PWSS under Jalpaiguri Division, P.H.E. Dte. |  |  | BILL/01063/2024-2025 | BP-2024-25-587 | 14/01/2025 | 14/01/2025 | IIT, KHARAGPUR | 7.08 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/19175 | Augmentation | Demand Note for payment of NPV and Cost of Compensatory Afforestation (FP/WB/WATER/495997/2024) |  |  | BILL/00252/2025-2026 | 78/25-26 | 11/07/2025 | 11/07/2025 | DIVISIONAL FOREST OFFICER, JALPAIGURI DIVISION | 10.92 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/19175 | Augmentation | Demand Note for payment of Cost of Boundary Pillars (FP/WB/WATER/495997/2024) |  |  | BILL/00253/2025-2026 | 79/25-26 | 10/07/2025 | 10/07/2025 | DIVISIONAL FOREST OFFICER, JALPAIGURI DIVISION | 4.37 | 0 | 0 | 0
Total | [13 empty] | 1099.8 | 37.49 | 3.41