## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Siliguri W/S Division | Augmentation of Porjhar Pipe Water Supply Scheme | SM/15302 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 2211/SWSD | 05/01/2023 | 05/01/2023 | Resource Division | 31.37 | 0 | 0 | 0
2 | JALPAIGURI |  | Siliguri W/S Division | Augmentation of Porjhar Pipe Water Supply Scheme | SM/15302 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF PORJHAR PIPED WATER SUPPLY SCHEME UNDER RAJGANJ BLOCK, JALPAIGURI DISTRICT UNDER SILIGURI W/S DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000071/2023-2024 | 264/SSD | 05/06/2023 | 15/06/2023 | ENVIROTECH SOLUTIONS | 2.77 | 2.77 | 100 | 30
3 | JALPAIGURI |  | Northern Mechanical | Augmentation of Porjhar Pipe Water Supply Scheme | SM/15302 | Augmentation | New Service Connection Charge for PORAJHAR, T/W No. II, under SHIVMANDIR CCC [APPLICATION NO. 4003332377 , Reference ID : 403156964] |  |  | BILL/02008/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.14 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Augmentation of Porjhar Pipe Water Supply Scheme | SM/15302 | Augmentation | New Service Connection Charge for PORAJHAR, T/W No. I, under SHIVMANDIR CCC [APPLICATION NO. 4003332364 , Reference ID : 403156961] |  |  | BILL/02007/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.78 | 0 | 0 | 0
5 | JALPAIGURI |  | Siliguri W/S Division | Augmentation of Porjhar Pipe Water Supply Scheme | SM/15302 | Augmentation | Laying distribution system,risingmain,installation of iron elemination plant, pump houses ,boundary walls ,functional house hold tap connection (FHTC) and other allied works under Jal Jeevan Mission (JJM) for Augmentation of PORJHAR Piped Water Supply Scheme under Rajganj Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000111/2023-2024 | 1158/SWSD | 09/08/2023 | 30/12/2025 | AKASH ENTERPRISE | 356.29 | 101.93 | 28.61 | 90
Total | [13 empty] | 401.34 | 104.7 | 26.09